## PDCA Main Page
PDCA Chart 05.02.2026
Problem
Missing milestones & timeliness
Scope
SF
Lane
| EUAP |  |  |  | Nov '25 | Dec '25 | Jan '26 | W5 | W6 | W7 | W8 F | W10 F | W12 F | W14 F | W16 | W18 F | YTD
Responsible |  |  | Completeness (Critical) |  | 82% | 84% | 84% |  |  |  | 85% | 87% | 89% | 91% | 85.6% | 95%
|  |  | Timeliness (Critical) |  | 10% | 22% | 48% |  |  |  | 66% | 69% | 73% | 78% | 55.66% | 80%
| Maersk MOF execution |  | Completeness (All) |  | N/A | N/A | 71% |  |  |  | 79% | 81% | 84% | 88% | 78.18% | 95%
|  |  | Timeliness (All) |  | N/A | N/A | 43% |  |  |  | 64% | 65% | 66% | 67% | 52.86% | 70%
|  |  | ETA accuracy 2P (SC4) |  |  |  | 38% | 44% | 62% | 39% | 65% | 68% | 70% | 72% | 40% | 76%
|  |  | ETA Accuracy 2D (SC4) |  |  |  | 11% | 13% | 17% | 17% | 20% | 25% | 40% | 50% | 9.14% | 72%
|  |  | SC4 Reference Completeness (CIV or DN) |  | N/A | N/A | 69% | 71% | 74% | 76% | 78% | 82% | 84% | 86% | 88.37% | 95%
Nr | Main Problems | Product Impact | Category |  | W01 | W02 | W03 | W04 | W05 | W06 | W07 | W10 | W12 | W14 | W16 | W18 | YTD
|  | high | Completeness (Critical) | [14 empty] | 0.4
|  | high | Timeliness (Critical) | [14 empty] | 0.2
|  | high | Completeness (Critical) | [14 empty] | 0.8
|  | high | Timeliness (Critical) | [14 empty] | 0.4
|  | high | Completeness (Critical) | [14 empty] | 1.2
|  | high | Timeliness (Critical) | [14 empty] | 1.4
|  | medium | Completeness (All) | [14 empty] | 0.6
|  | medium | Timeliness (All) | [14 empty] | 0.7
|  | medium | Completeness (All) | [14 empty] | 0.5
|  | medium | Timeliness (All) | [14 empty] | 1
|  | medium | Completeness (All) | [14 empty] | 0.4
|  | medium | Timeliness (All) | [14 empty] | 0.8
|  | medium | Completeness (All) | [14 empty] | 0.8
|  | medium | Timeliness (All) | [14 empty] | 1
|  | medium | Completeness (All) | [14 empty] | 1.1
|  | medium | Timeliness (All) | [14 empty] | 1.3
|  | medium | Completeness (All) | [14 empty] | 0.3
|  | medium | Timeliness (All) | [14 empty] | 1
|  | high | Completeness (Critical) | [14 empty] | 0.7
|  | high | Timeliness (Critical) | [14 empty] | 0.2
|  | high | Completeness (Critical) | [14 empty] | 0.4
|  | high | Timeliness (Critical) | [14 empty] | 0.5
|  | high | Completeness (Critical) | [14 empty] | 0.1
|  | high | Timeliness (Critical) | [14 empty] | 1.1
|  | high | Completeness (Critical) | [14 empty] | 0.8
|  | high | Timeliness (Critical) | [14 empty] | 1.5
|  | medium | Completeness (All) | [14 empty] | 0.8
|  | medium | Timeliness (All) | [14 empty] | 1
|  | medium | Completeness (All) | [14 empty] | 0.6
|  | medium | Timeliness (All) | [14 empty] | 1.2
|  | medium | Completeness (All) | [14 empty] | 0.5
|  | medium | Timeliness (All) | [14 empty] | 1
|  | medium | Completeness (All) | [14 empty] | 0.4
|  | medium | Timeliness (All) | [14 empty] | 0.5
|  | high | Completeness (Critical) | [14 empty] | 1
|  | high | Timeliness (Critical) | [14 empty] | 0.8
|  | medium | Completeness (All) | [14 empty] | 1.5
|  | medium | Timeliness (All) | [14 empty] | 1.8
|  | high | Completeness (Critical) | [14 empty] | 0.1
|  | high | Timeliness (Critical) | [14 empty] | 0.5
|  | high | Completeness (Critical) | [14 empty] | 0.7
|  | high | Timeliness (Critical) | [14 empty] | 1.8
|  | medium | Completeness (All) | [14 empty] | 0.1
|  | medium | Timeliness (All) | [14 empty] | 0.5
|  | medium | Completeness (All) | [14 empty] | 1.6
|  | medium | Timeliness (All) | [14 empty] | 0.9
|  | high | Completeness (Critical) | [14 empty] | 1.2
|  | high | Timeliness (Critical) | [14 empty] | 1.4
|  | high | Completeness (Critical) | [14 empty] | 1.1
|  | high | Timeliness (Critical) | [14 empty] | 1.1
|  | medium | Completeness (All) | [14 empty] | 0.7
|  | medium | Timeliness (All) | [14 empty] | 0.7
|  | medium | Completeness (All) | [14 empty] | 0.9
|  | medium | Timeliness (All) | [14 empty] | 0.7
|  | medium | Completeness (All) | [14 empty] | 0.8
|  | medium | Timeliness (All) | [14 empty] | 0.6
|  | high | Completeness (Critical) | [14 empty] | 0.7
|  | high | Timeliness (Critical) | [14 empty] | 0.2
|  | high | Completeness (Critical) | [14 empty] | 0.7
|  | high | Timeliness (Critical) | [14 empty] | 0.2
|  | high | Completeness (Critical) | [14 empty] | 0.6
|  | high | Timeliness (Critical) | [14 empty] | 0.1
|  | high | Completeness (Critical) | [14 empty] | 0.6
|  | high | Timeliness (Critical) | [14 empty] | 0.2
|  | medium | Completeness (All) | [14 empty] | 1.6
|  | medium | Timeliness (All) | [14 empty] | 1.9
|  | medium | Completeness (All) | [14 empty] | 1.3
|  | medium | Timeliness (All) | [14 empty] | 1.1
|  | medium | Completeness (All) | [14 empty] | 0.2
|  | medium | Timeliness (All) | [14 empty] | 0.1
|  | high | Completeness (Critical) | [14 empty] | 1.8
|  | high | Timeliness (Critical) | [14 empty] | 1.5
|  | high | Completeness (Critical) | [14 empty] | 0.9
|  | high | Timeliness (Critical) | [14 empty] | 0.8
|  | medium | Completeness (All) | [14 empty] | 1.1
|  | medium | Timeliness (All) | [14 empty] | 0.7
|  | high | Completeness (Critical) | [14 empty] | 1.8
|  | high | Timeliness (Critical) | [14 empty] | 1.5
|  | high | Completeness (Critical) | [14 empty] | 1.7
|  | high | Timeliness (Critical) | [14 empty] | 1.1
|  | medium | Completeness (All) | [14 empty] | 0.8
|  | medium | Timeliness (All) | [14 empty] | 0.4
|  | medium | ETA accuracy 2P |  | 22.3% | 38.6% | 40.3% | 43.4% | 43.5% | 62.2% | 39.2% | [6 empty] | 0.6
|  | medium | ETA accuracy 2P |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
|  | medium | ETA accuracy 2D |  | 4.4% | 13.2% | 7% | 11.5% | 12.5% | 17.4% | 17.4% | [6 empty] | 2.2
|  | medium | ETA accuracy 2D |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
87 | SC4 - Shipment data received by Bosch doesn't have the CIV or DN reference | high | Reference Completeness (SC4) |  | 71.4% | 63.8% | 72% | 70.2% | 67.9% | 75.2% | 77.7% | [6 empty] | 0.8
88 | SC4 - Shipment data received by Bosch has the CIV or DN reference but do not have the correct data | medium | Reference Quality (SC4) |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
89 | Milestones sent to Bosch do not follow a plausible date order because CW1 lacks chronological sequence validation and manaual error occurs | medium | Plausability (% of shipments with ≥1 sequence break) |  | 25.56% | 17.08% | 14.88% | 14.55% | 12.45% | 7.08% | 10.19% | [6 empty] | -0.4
Nr. | Measures | Link to main problems | Category | Responsible | [12 empty] | Impact (%) | Status | Action | Review
[7 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
[17 empty] | 8-12% | P | Immediate | Mar | bar: Feb to Mar
|  |  |  | Maersk ( Akhil) | [12 empty] | 10-15% | P | Immediate | Mar | bar: Feb to Mar
|  |  |  | Maersk (Timmy) | [12 empty] | 85-90% | P | Mar | Mar | bar: Mar to Apr
|  |  |  | Bosch | [12 empty] | 4-8%
|  |  |  | Bosch | [12 empty] | 10-14%
|  |  |  | Bosch | [12 empty] | 10-12%
|  |  |  | Maersk (Timmy) | [12 empty] | 8-12% | P | Mar | Mar | bar: Mar to Apr
|  |  |  | Maersk (Timmy) | [12 empty] | 5-8% | P | Mar | Mar | bar: Mar to Apr
|  |  |  | Maersk (Harsh) | [12 empty] | 5-7% | P | Mar | Mar | bar: Mar to Apr
|  |  |  | Maersk ( Josh) | [12 empty] | 2-4% | P | Mar | Mar | bar: Mar to Apr
|  |  |  | Maersk ( Josh) | [12 empty] | 2-4% | P | Mar | Mar | bar: Mar to Apr
|  |  |  | MAersk ( Jacob) | [12 empty] | 5-7% | P | Mar | Mar | bar: Mar to Apr
|  |  |  | Maersk (Timmy) | [12 empty] | 5-7% | P | Mar | Mar | bar: Mar to Apr
|  |  |  | Maersk ( Alberto) | [12 empty] | 5-8% | P | Mar | Mar | bar: Mar to Apr
|  |  |  | Maersk ( CT tower - Stefan K) | [12 empty] | 5-8% | P | Mar | Apr | bar: Feb; Apr
Maersk ( CT tower - Stefan K) | bar: Feb; Apr
Maersk ( CT tower - Stefan K) | bar: Mar to Apr
Maersk (Timmy) | bar: Mar to Apr
[17 empty] | 4-6% | P | Feb | May
Status: | [6 empty] | Feb: Measure:
P C Activity finished | P = Responsibility and due date defined | D | D = Activity finished |  |  |  | Feb: r; Mar: r = Planned beginning; Jul: s; Aug: s = Planned end
C | C = Intermediate result achieved | A | A = Effectiveness proven |  |  |  | Feb: p; Mar: p = Actual beginning; Jul: q; Aug: q = Actual end
Timeline
measurements & solution
What is it for them
Note on C17: - low (minor business impact, e. g.: loss of BI tool) - medium (medium business impact, e. g.: loss of engineering software, loss of Skype) - high (major business impact, e. g.: loss of ERP system) - unknown
Note on D137: Dudek Jaroslaw (GS/PSD32): MRC Managerial Root Caus TRC Technical Root Cause Bug-Fix Others
Note on S137: Estimated impact of measure on overall performance.

## SC4 Data
SC4 - Weekly Milestone Data
Critical Milestones: S00, S02, S04, S07, S31, S45
|  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 16
Milestone | Type | Required | Available | In Time | Completeness | Timeliness | Required | Available | In Time | Completeness | Timeliness | Required | Available | In Time | Completeness | Timeliness | Required | Available | In Time | Completeness | Timeliness | Required | Available | In Time | Completeness | Timeliness | Required | Available | In Time | Completeness | Timeliness | Required | Available | In Time | Completeness | Timeliness | Required | Available | In Time | Completeness | Timeliness
S00 - Shipment created | Actual | 168 | 88 | 88 | 52% | 52% | 390 | 141 | 139 | 36% | 36% | 675 | 236 | 233 | 35% | 35% | 719 | 358 | 352 | 50% | 49% | 527 | 291 | 288 | 55.22% | 54.65% | 569 | 349 | 341 | 61% | 60% | 566 | 436 | 423 | 77.03% | 74.73% | 389 | 350 | 318 | 0.8997 | 0.8175
S02 - Collected | Estimated | 145 | 114 | 59 | 79% | 41% | 286 | 237 | 104 | 83% | 36% | 496 | 423 | 167 | 85% | 34% | 514 | 447 | 220 | 87% | 43% | 398 | 337 | 210 | 84.67% | 52.76% | 399 | 359 | 234 | 90% | 59% | 446 | 395 | 297 | 88.57% | 66.59% | 267 | 253 | 230 | 0.9476 | 0.8614
S02 - Collected | Actual | 145 | 133 | 24 | 92% | 17% | 286 | 272 | 112 | 95% | 39% | 496 | 438 | 171 | 88% | 34% | 514 | 462 | 207 | 90% | 40% | 398 | 354 | 131 | 88.94% | 32.91% | 399 | 361 | 149 | 90% | 37% | 446 | 405 | 171 | 90.81% | 38.34% | 267 | 222 | 111 | 0.8315 | 0.4157
S46 - Documents rcvd from shipper | Actual | 168 | 103 | 45 | 61% | 27% | 390 | 144 | 72 | 37% | 18% | 675 | 277 | 104 | 41% | 15% | 719 | 435 | 226 | 61% | 31% | 527 | 357 | 165 | 67.74% | 31.31% | 569 | 418 | 235 | 73% | 41% | 566 | 465 | 288 | 82.16% | 50.88% | 389 | 351 | 232 | 0.9023 | 0.5964
S10 - On hand at origin SVC | Actual | 154 | 148 | 98 | 96% | 64% | 335 | 305 | 177 | 91% | 53% | 535 | 443 | 274 | 83% | 51% | 577 | 505 | 281 | 88% | 49% | 412 | 335 | 194 | 81.31% | 47.09% | 461 | 413 | 243 | 90% | 53% | 473 | 433 | 268 | 91.54% | 56.66% | 327 | 292 | 154 | 0.893 | 0.4709
S11 - On hand at origin Hub/ CC | Actual | 154 | 104 | 73 | 68% | 47% | 335 | 146 | 92 | 44% | 27% | 535 | 245 | 160 | 46% | 30% | 577 | 390 | 205 | 68% | 36% | 412 | 292 | 164 | 70.87% | 39.81% | 461 | 376 | 207 | 82% | 45% | 473 | 420 | 252 | 88.79% | 53.28% | 327 | 291 | 150 | 0.8899 | 0.4587
S16 - Shipment booked with carrier | Actual | 168 | 119 | 86 | 71% | 51% | 390 | 237 | 183 | 61% | 47% | 675 | 415 | 323 | 61% | 48% | 719 | 539 | 439 | 75% | 61% | 527 | 405 | 322 | 76.85% | 61.1% | 569 | 451 | 384 | 79% | 67% | 566 | 477 | 381 | 84.28% | 67.31% | 389 | 345 | 323 | 0.8869 | 0.8303
S17 - Tendered carrier | Actual | 154 | 108 | 44 | 70% | 29% | 335 | 141 | 89 | 42% | 27% | 535 | 225 | 89 | 42% | 17% | 577 | 328 | 172 | 57% | 30% | 412 | 245 | 135 | 59.47% | 32.77% | 461 | 286 | 165 | 62% | 36% | 473 | 326 | 129 | 68.92% | 27.27% | 327 | 245 | 185 | 0.7492 | 0.5657
S50 - Received origin CFS | Actual | 115 | 104 | 46 | 90% | 40% | 190 | 175 | 122 | 92% | 64% | 354 | 273 | 149 | 77% | 42% | 294 | 208 | 96 | 71% | 33% | 223 | 176 | 98 | 78.92% | 43.95% | 183 | 122 | 81 | 67% | 44% | 263 | 229 | 76 | 87.07% | 28.9% | 134 | 94 | 73 | 0.7015 | 0.5448
S04 - Vessel/ flight departed | Estimated | 168 | 166 | 63 | 99% | 38% | 390 | 385 | 166 | 99% | 43% | 675 | 648 | 248 | 96% | 37% | 719 | 696 | 308 | 97% | 43% | 527 | 504 | 257 | 95.64% | 48.77% | 569 | 551 | 303 | 97% | 53% | 566 | 542 | 408 | 95.76% | 72.08% | 389 | 383 | 310 | 0.9846 | 0.7969
S04 - Vessel/ flight departed | Actual | 168 | 161 | 140 | 96% | 83% | 390 | 362 | 213 | 93% | 55% | 675 | 563 | 353 | 83% | 52% | 719 | 630 | 385 | 88% | 54% | 527 | 471 | 259 | 89.37% | 49.15% | 569 | 500 | 332 | 88% | 58% | 566 | 525 | 359 | 92.76% | 63.43% | 389 | 357 | 132 | 0.9177 | 0.3393
S07 - Vessel/ flight arrived | Estimated | 168 | 168 | 43 | 100% | 26% | 390 | 376 | 83 | 96% | 21% | 675 | 631 | 124 | 93% | 18% | 719 | 679 | 159 | 94% | 22% | 527 | 489 | 113 | 92.79% | 21.44% | 569 | 547 | 75 | 96% | 13% | 566 | 552 | 139 | 97.53% | 24.56% | 389 | 380 | 161 | 0.9769 | 0.4139
S07 - Vessel/ flight arrived | Actual | 168 | 140 | 55 | 83% | 33% | 390 | 325 | 256 | 83% | 66% | 675 | 544 | 409 | 81% | 61% | 719 | 607 | 373 | 84% | 52% | 527 | 431 | 231 | 81.78% | 43.83% | 569 | 502 | 261 | 88% | 46% | 566 | 488 | 258 | 86.22% | 45.58% | 389 | 212 | 69 | 0.545 | 0.1774
S51 - Arrived destination CFS | Actual | 115 | 75 | 69 | 65% | 60% | 190 | 73 | 58 | 38% | 31% | 354 | 102 | 23 | 29% | 6% | 294 | 120 | 75 | 41% | 26% | 223 | 78 | 31 | 34.98% | 13.9% | 183 | 74 | 52 | 40% | 28% | 263 | 153 | 84 | 58.17% | 31.94% | 134 | 24 | 18 | 0.1791 | 0.1343
S18 - Recovered from carrier | Actual | 53 | 12 | 2 | 23% | 4% | 200 | 25 | 12 | 13% | 6% | 321 | 98 | 57 | 31% | 18% | 425 | 258 | 160 | 61% | 38% | 304 | 194 | 93 | 63.82% | 30.59% | 386 | 316 | 145 | 82% | 38% | 303 | 244 | 121 | 80.53% | 39.93% | 255 | 130 | 74 | 0.5098 | 0.2902
S12 - On hand at destination Hub/ CC | Actual | 53 | 15 | 3 | 28% | 6% | 200 | 67 | 30 | 34% | 15% | 321 | 158 | 79 | 49% | 25% | 425 | 311 | 174 | 73% | 41% | 304 | 212 | 95 | 69.74% | 31.25% | 386 | 335 | 142 | 87% | 37% | 303 | 256 | 126 | 84.49% | 41.58% | 255 | 169 | 81 | 0.6627 | 0.3176
S13 - On hand at destination SVC | Actual | 53 | 15 | 2 | 28% | 4% | 200 | 27 | 16 | 14% | 8% | 321 | 110 | 70 | 34% | 22% | 425 | 281 | 213 | 66% | 50% | 304 | 213 | 138 | 70.07% | 45.39% | 386 | 337 | 235 | 87% | 61% | 303 | 266 | 198 | 87.79% | 65.35% | 255 | 170 | 91 | 0.6667 | 0.3569
S45 - Handover to broker | Actual | 118 | 118 | 118 | 100% | 100% | 129 | 129 | 119 | 100% | 92% | 213 | 120 | 116 | 56% | 54% | 184 | 77 | 68 | 42% | 37% | 109 | 52 | 52 | 47.71% | 47.71% | 110 | 23 | 23 | 21% | 21% | 193 | 56 | 54 | 29.02% | 27.98% | 44 | 13 | 2 | 0.2955 | 0.0455
S05 - In delivery | Actual | 50 | 10 | 9 | 20% | 18% | 261 | 22 | 19 | 8% | 7% | 462 | 49 | 18 | 11% | 4% | 535 | 69 | 12 | 13% | 2% | 418 | 73 | 37 | 17.46% | 8.852% | 459 | 55 | 24 | 12% | 5% | 373 | 78 | 27 | 20.91% | 7.239% | 345 | 7 | 2 | 0.0203 | 0.0058
S31 - Delivered | Estimated | 50 | 48 | 40 | 96% | 80% | 261 | 258 | 214 | 99% | 82% | 462 | 449 | 325 | 97% | 70% | 535 | 522 | 358 | 98% | 67% | 418 | 400 | 288 | 95.69% | 68.9% | 459 | 430 | 309 | 94% | 67% | 373 | 355 | 271 | 95.17% | 72.65% | 345 | 342 | 265 | 0.9913 | 0.7681
S31 - Delivered | Actual | 50 | 50 | 2 | 100% | 4% | 261 | 261 | 32 | 100% | 12% | 462 | 353 | 132 | 76% | 29% | 535 | 445 | 48 | 83% | 9% | 418 | 351 | 44 | 83.97% | 10.53% | 459 | 304 | 73 | 66% | 16% | 373 | 267 | 49 | 71.58% | 13.14% | 345 | 208 | 3 | 0.6029 | 0.0087
[19 empty] | SC3+ SC4 |  | critical
all

## SC3 Data
SC3 - Weekly Milestone Data
Critical Milestones: S02, S04, S07, S31, S45
|  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 16
Milestone | Type | Required | Available | In Time | Completeness | Timeliness | Required | Available | In Time | Completeness | Timeliness | Required | Available | In Time | Completeness | Timeliness | Required | Available | In Time | Completeness | Timeliness | Required | Available | In Time | Completeness | Timeliness | Required | Available | In Time | Completeness | Timeliness | Required | Available | In Time | Completeness | Timeliness | Required | Available | In Time | Completeness | Timeliness
S60 - Pre-Booking confirmed | Actual | 29 | 27 | 27 | 93.1% | 93.1% | 36 | 33 | 33 | 91.7% | 91.7% | 51 | 47 | 47 | 92.2% | 92.2% | 66 | 63 | 62 | 95.5% | 93.9% | 52 | 48 | 48 | 92.31% | 92.31% | 76 | 70 | 70 |  |  | 74 | 69 | 67 | 93.24% | 90.54% | 82 | 82 | 82 | 1 | 1
S52 - Empty Container picked up | Actual | 26 | 7 | 5 | 26.9% | 19.2% | 27 | 8 | 6 | 29.6% | 22.2% | 47 | 14 | 12 | 29.8% | 25.5% | 52 | 10 | 6 | 19.2% | 11.5% | 45 | 13 | 11 | 28.89% | 24.44% | 46 | 14 | 6 |  |  | 64 | 22 | 16 | 34.38% | 25% | 75 | 32 | 15 | 0.4267 | 0.2
S02 - Collected | Actual | 240 | 195 | 76 | 81.3% | 31.7% | 283 | 224 | 111 | 79.2% | 39.2% | 289 | 211 | 92 | 73% | 31.8% | 306 | 242 | 97 | 79.1% | 31.7% | 292 | 221 | 100 | 75.68% | 34.25% | 304 | 239 | 117 |  |  | 322 | 251 | 131 | 77.95% | 40.68% | 335 | 260 | 131 | 0.7761 | 0.391
S02 - Collected | Estimated | 214 | 174 | 0 | 81.3% | 0% | 256 | 207 | 0 | 80.9% | 0% | 242 | 188 | 0 | 77.7% | 0% | 254 | 213 | 0 | 83.9% | 0% | 247 | 205 | 0 | 83% | 0% | 258 | 219 | 0 |  |  | 258 | 223 | 0 | 86.43% | 0% | 260 | 216 | 0 | 0.8308 | 0
S10 - On hand at origin SVC | Actual | 146 | 138 | 95 | 94.5% | 65.1% | 208 | 194 | 114 | 93.3% | 54.8% | 181 | 162 | 105 | 89.5% | 58% | 198 | 176 | 97 | 88.9% | 49% | 183 | 171 | 108 | 93.44% | 59.02% | 216 | 195 | 104 |  |  | 213 | 192 | 114 | 90.14% | 53.52% | 208 | 193 | 111 | 0.9279 | 0.5337
S50 - Received origin CFS | Actual | 107 | 84 | 75 | 78.5% | 70.1% | 115 | 90 | 82 | 78.3% | 71.3% | 125 | 97 | 84 | 77.6% | 67.2% | 153 | 106 | 100 | 69.3% | 65.4% | 147 | 117 | 104 | 79.59% | 70.75% | 150 | 96 | 74 |  |  | 130 | 79 | 55 | 60.77% | 42.31% | 176 | 140 | 120 | 0.7955 | 0.6818
S53 - Full Container loaded on vessel | Actual | 29 | 12 | 11 | 41.4% | 37.9% | 36 | 15 | 14 | 41.7% | 38.9% | 51 | 26 | 25 | 51% | 49% | 66 | 28 | 23 | 42.4% | 34.8% | 54 | 37 | 34 | 68.52% | 62.96% | 78 | 46 | 43 |  |  | 82 | 42 | 30 | 51.22% | 36.59% | 82 | 69 | 66 | 0.8415 | 0.8049
S04 - Vessel/ flight departed | Actual | 253 | 219 | 217 | 86.6% | 85.8% | 323 | 279 | 277 | 86.4% | 85.8% | 306 | 258 | 250 | 84.3% | 81.7% | 351 | 281 | 274 | 80.1% | 78.1% | 330 | 301 | 294 | 91.21% | 89.09% | 366 | 311 | 304 |  |  | 343 | 283 | 277 | 82.51% | 80.76% | 382 | 351 | 332 | 0.9188 | 0.8691
S04 - Vessel/ flight departed | Estimated | 253 | 219 | 174 | 86.6% | 68.8% | 323 | 289 | 234 | 89.5% | 72.4% | 306 | 264 | 216 | 86.3% | 70.6% | 351 | 297 | 239 | 84.6% | 68.1% | 330 | 301 | 268 | 91.21% | 81.21% | 366 | 307 | 259 |  |  | 343 | 288 | 261 | 83.97% | 76.09% | 382 | 344 | 295 | 0.9005 | 0.7723
S07 - Vessel/ flight arrived | Actual | 253 | 229 | 224 | 90.5% | 88.5% | 323 | 291 | 287 | 90.1% | 88.9% | 306 | 264 | 260 | 86.3% | 85% | 351 | 302 | 298 | 86% | 84.9% | 330 | 308 | 307 | 93.33% | 93.03% | 366 | 320 | 316 |  |  | 343 | 303 | 301 | 88.34% | 87.76% | 382 | 353 | 345 | 0.9241 | 0.9031
S07 - Vessel/ flight arrived | Estimated | 253 | 223 | 211 | 88.1% | 83.4% | 323 | 295 | 279 | 91.3% | 86.4% | 306 | 269 | 254 | 87.9% | 83% | 351 | 304 | 290 | 86.6% | 82.6% | 330 | 309 | 294 | 93.64% | 89.09% | 366 | 325 | 303 |  |  | 343 | 303 | 272 | 88.34% | 79.3% | 382 | 358 | 348 | 0.9372 | 0.911
S54 - Full Container discharge from vessel | Actual | 29 | 4 | 2 | 13.8% | 6.9% | 36 | 5 | 5 | 13.9% | 13.9% | 51 | 2 | 0 | 3.9% | 0% | 66 | 3 | 3 | 4.5% | 4.5% | 54 | 4 | 3 | 7.407% | 5.556% | 78 | 2 | 2 |  |  | 82 | 10 | 6 | 12.2% | 7.317% | 82 | 18 | 18 | 0.2195 | 0.2195
S51 - Arrived destination CFS | Actual | 107 | 44 | 9 | 41.1% | 8.4% | 115 | 49 | 8 | 42.6% | 7% | 125 | 39 | 7 | 31.2% | 5.6% | 153 | 61 | 42 | 39.9% | 27.5% | 147 | 63 | 55 | 42.86% | 37.41% | 150 | 47 | 42 |  |  | 130 | 29 | 25 | 22.31% | 19.23% | 176 | 83 | 78 | 0.4716 | 0.4432
S13 - On hand at destination SVC | Actual | 146 | 12 | 9 | 8.2% | 6.2% | 208 | 38 | 36 | 18.3% | 17.3% | 181 | 75 | 66 | 41.4% | 36.5% | 198 | 118 | 108 | 59.6% | 54.5% | 183 | 147 | 132 | 80.33% | 72.13% | 216 | 182 | 170 |  |  | 213 | 192 | 179 | 90.14% | 84.04% | 206 | 191 | 168 | 0.9272 | 0.8155
S45 - Handover to broker | Actual | 111 | 41 | 41 | 36.9% | 36.9% | 111 | 31 | 31 | 27.9% | 27.9% | 106 | 43 | 42 | 40.6% | 39.6% | 124 | 58 | 56 | 46.8% | 45.2% | 127 | 56 | 53 | 44.09% | 41.73% | 115 | 53 | 49 |  |  | 94 | 40 | 36 | 42.55% | 38.3% | 151 | 106 | 102 | 0.702 | 0.6755
S45 - Handover to broker | Estimated | 33 | 3 | 3 | 9.1% | 9.1% | 32 | 8 | 8 | 25% | 25% | 32 | 12 | 12 | 37.5% | 37.5% | 37 | 19 | 17 | 51.4% | 45.9% | 34 | 21 | 20 | 61.76% | 58.82% | 43 | 28 | 25 |  |  | 46 | 22 | 21 | 47.83% | 45.65% | 151 | 81 | 52 | 0.5364 | 0.3444
S05 - In delivery | Actual | 187 | 74 | 44 | 39.6% | 23.5% | 259 | 135 | 59 | 52.1% | 22.8% | 248 | 109 | 63 | 44% | 25.4% | 278 | 133 | 96 | 47.8% | 34.5% | 258 | 143 | 113 | 55.43% | 43.8% | 312 | 177 | 162 |  |  | 297 | 192 | 171 | 64.65% | 57.58% | 295 | 231 | 181 | 0.7831 | 0.6136
S31 - Delivered | Actual | 187 | 79 | 27 | 42.2% | 14.4% | 259 | 149 | 40 | 57.5% | 15.4% | 248 | 134 | 25 | 54% | 10.1% | 278 | 162 | 26 | 58.3% | 9.4% | 258 | 146 | 33 | 56.59% | 12.79% | 312 | 179 | 59 |  |  | 297 | 180 | 42 | 60.61% | 14.14% | 295 | 216 | 81 | 0.7322 | 0.2746
S31 - Delivered | Estimated | 187 | 135 | 108 | 72.2% | 57.8% | 259 | 198 | 152 | 76.4% | 58.7% | 248 | 172 | 125 | 69.4% | 50.4% | 278 | 197 | 130 | 70.9% | 46.8% | 258 | 173 | 125 | 67.05% | 48.45% | 312 | 202 | 141 |  |  | 297 | 195 | 149 | 65.66% | 50.17% | 295 | 230 | 143 | 0.7797 | 0.4847
S55 - Empty Container returned | Actual | 28 | 10 | 7 | 35.7% | 25% | 36 | 24 | 20 | 66.7% | 55.6% | 50 | 31 | 26 | 62% | 52% | 64 | 42 | 40 | 65.6% | 62.5% | 52 | 40 | 40 | 76.92% | 76.92% | 77 | 61 | 60 |  |  | 80 | 55 | 54 | 68.75% | 67.5% | 82 | 74 | 72 | 0.9024 | 0.878

## Mapping Prob-Root
Nr. | Code | Description | Metric |  |  | type | Error | Rootcause | Measure 1 | Measure 2 | Measure 3 | Main problem
1 | SC4 – S00 | Shipment created (Actual) | Completeness (Critical) | Critical) | Actual) |  |  | CW1 configurations are not set up correctly to handle Bosch requirements |  |  | Review the legacy system shipments flow for the branch in Japan
2 | SC4 – S00 | Shipment created (Actual) | Timeliness (Critical) | Critical) | Actual) |  |  | CW1 configurations are not set up correctly to handle Bosch requirements |  |  | Review the legacy system shipments flow for the branch in Japan
3 | SC4 – S02 | Collected (Estimated) | Completeness (Critical) | Critical) | Estimated) |  |  | Manual milestones not updated on time by Operators due to lack of resources
4 | SC4 – S02 | Collected (Estimated) | Timeliness (Critical) | Critical) | Estimated) |  |  | Manual milestones not updated on time by Operators due to lack of resources
5 | SC4 – S02 | Collected (Actual) | Completeness (Critical) | Critical) | Actual) |  |  | Manual milestones not updated on time by Operators due to lack of resources
6 | SC4 – S02 | Collected (Actual) | Timeliness (Critical) | Critical) | Actual) |  |  | Manual milestones not updated on time by Operators due to lack of resources
7 | SC4 – S46 | Documents rcvd from shipper (Actual) | Completeness (All) | All) | Actual) |  |  | SOP to fill CW1 fields are not followed by Operators due to lack of resources
8 | SC4 – S46 | Documents rcvd from shipper (Actual) | Timeliness (All) | All) | Actual) |  |  | SOP to fill CW1 fields are not followed by Operators due to lack of resources
9 | SC4 – S10 | On hand at origin SVC (Actual) | Completeness (All) | All) | Actual) |  |  | Manual milestones not updated on time by Operators due to lack of resources
10 | SC4 – S10 | On hand at origin SVC (Actual) | Timeliness (All) | All) | Actual) |  |  | Manual milestones not updated on time by Operators due to lack of resources
11 | SC4 – S11 | On hand at origin Hub/CC (Actual) | Completeness (All) | All) | Actual)
12 | SC4 – S11 | On hand at origin Hub/CC (Actual) | Timeliness (All) | All) | Actual) |  |  | Manual milestones not updated on time by Operators due to lack of resources
13 | SC4 – S16 | Shipment booked with carrier (Actual) | Completeness (All) | All) | Actual) |  |  | SOP to fill CW1 fields are not followed by Operators due to lack of resources
14 | SC4 – S16 | Shipment booked with carrier (Actual) | Timeliness (All) | All) | Actual) |  |  | Manual milestones not updated on time by Operators due to lack of resources
15 | SC4 – S17 | Tendered carrier (Actual) | Completeness (All) | All) | Actual) |  |  | CW1 configurations are not set up correctly to handle Bosch requirements
16 | SC4 – S17 | Tendered carrier (Actual) | Timeliness (All) | All) | Actual) |  |  | CW1 configurations are not set up correctly to handle Bosch requirements
17 | SC4 – S50 | Received origin CFS (Actual) | Completeness (All) | All) | Actual) |  |  | SOP to fill CW1 fields are not followed by Operators due to lack of resources
18 | SC4 – S50 | Received origin CFS (Actual) | Timeliness (All) | All) | Actual) |  |  | CW1 configurations are not set up correctly to handle Bosch requirements
19 | SC4 – S04 | Vessel/flight departed (Estimated) | Completeness (Critical) | Critical) | Estimated) |  |  | The Consol is not attached to shipment with "is Linked" Flag
20 | SC4 – S04 | Vessel/flight departed (Estimated) | Timeliness (Critical) | Critical) | Estimated) |  |  | The Consol is not attached to shipment with "is Linked" Flag
21 | SC4 – S04 | Vessel/flight departed (Actual) | Completeness (Critical) | Critical) | Actual) |  |  | The Consol is not attached to shipment with "is Linked" Flag
22 | SC4 – S04 | Vessel/flight departed (Actual) | Timeliness (Critical) | Critical) | Actual) |  |  | The Consol is not attached to shipment with "is Linked" Flag
23 | SC4 – S07 | Vessel/flight arrived (Estimated) | Completeness (Critical) | Critical) | Estimated) |  |  | The Consol is not attached to shipment with "is Linked" Flag
24 | SC4 – S07 | Vessel/flight arrived (Estimated) | Timeliness (Critical) | Critical) | Estimated) |  |  | The Consol is not attached to shipment with "is Linked" Flag
25 | SC4 – S07 | Vessel/flight arrived (Actual) | Completeness (Critical) | Critical) | Actual) |  |  | The Consol is not attached to shipment with "is Linked" Flag
26 | SC4 – S07 | Vessel/flight arrived (Actual) | Timeliness (Critical) | Critical) | Actual) |  |  | The Consol is not attached to shipment with "is Linked" Flag
27 | SC4 – S51 | Arrived destination CFS (Actual) | Completeness (All) | All) | Actual) |  |  | The Automation of the Milestones is not working based the DEX events
28 | SC4 – S51 | Arrived destination CFS (Actual) | Timeliness (All) | All) | Actual) |  |  | The Automation of the Milestones is not working based the DEX events
29 | SC4 – S18 | Recovered from carrier (Actual) | Completeness (All) | All) | Actual) |  |  | CW1 configurations are not set up correctly to handle Bosch requirements
30 | SC4 – S18 | Recovered from carrier (Actual) | Timeliness (All) | All) | Actual) |  |  | CW1 configurations are not set up correctly to handle Bosch requirements
31 | SC4 – S12 | On hand at destination Hub/CC (Actual) | Completeness (All) | All) | Actual) |  |  | Milestone is dependent on Manual input and is missed due to Lack of resources
32 | SC4 – S12 | On hand at destination Hub/CC (Actual) | Timeliness (All) | All) | Actual) |  |  | Milestone is dependent on Manual input and is missed due to Lack of resources
33 | SC4 – S13 | On hand at destination SVC (Actual) | Completeness (All) | All) | Actual) |  |  | SOP to fill CW1 fields are not followed by Operators due to lack of resources
34 | SC4 – S13 | On hand at destination SVC (Actual) | Timeliness (All) | All) | Actual) |  |  | Milestone is dependent on Manual input and is missed due to Lack of resources
35 | SC4 – S45 | Handover to broker (Actual) | Completeness (Critical) | Critical) | Actual) |  |  | The HBL div mode is changed after receiving
36 | SC4 – S45 | Handover to broker (Actual) | Timeliness (Critical) | Critical) | Actual) |  |  | The HBL div mode is changed after receiving
37 | SC4 – S05 | In delivery (Actual) | Completeness (All) | All) | Actual) |  |  | CW1 configurations are not set up correctly to handle Bosch requirements
38 | SC4 – S05 | In delivery (Actual) | Timeliness (All) | All) | Actual) |  |  | CW1 configurations are not set up correctly to handle Bosch requirements
39 | SC4 – S31 | Delivered (Estimated) | Completeness (Critical) | Critical) | Estimated) |  |  | Milestone is dependent on Manual input and is missed due to Lack of resources
40 | SC4 – S31 | Delivered (Estimated) | Timeliness (Critical) | Critical) | Estimated) |  |  | Milestone is dependent on Manual input and is missed due to Lack of resources
41 | SC4 – S31 | Delivered (Actual) | Completeness (Critical) | Critical) | Actual) |  |  | Milestone is dependent on Manual input and is missed due to Lack of resources
42 | SC4 – S31 | Delivered (Actual) | Timeliness (Critical) | Critical) | Actual) |  |  | Milestone is dependent on Manual input and is missed due to Lack of resources
43 | SC3 – S60 | Pre Booking confirmed (Actual) | Completeness (All) | All) | Actual)
44 | SC3 – S60 | Pre Booking confirmed (Actual) | Timeliness (All) | All) | Actual)
45 | SC3 – S52 | Empty Container picked up (Actual) | Completeness (All) | All) | Actual) |  |  | CW1 configurations are not set up correctly to handle Bosch requirements
46 | SC3 – S52 | Empty Container picked up (Actual) | Timeliness (All) | All) | Actual) |  |  | CW1 configurations are not set up correctly to handle Bosch requirements
47 | SC3 – S02 | Collected (Actual) | Completeness (Critical) | Critical) | Actual) |  |  | Manual milestones not updated on time by Operators due to lack of resources
48 | SC3 – S02 | Collected (Actual) | Timeliness (Critical) | Critical) | Actual) |  |  | Manual milestones not updated on time by Operators due to lack of resources
49 | SC3 – S02 | Collected (Estimated) | Completeness (Critical) | Critical) | Estimated) |  |  | Manual milestones not updated on time by Operators due to lack of resources
50 | SC3 – S02 | Collected (Estimated) | Timeliness (Critical) | Critical) | Estimated) |  |  | Manual milestones not updated on time by Operators due to lack of resources
51 | SC3 – S10 | On hand at origin SVC (Actual) | Completeness (All) | All) | Actual) |  |  | SOP to fill CW1 fields are not followed by Operators due to lack of resources
52 | SC3 – S10 | On hand at origin SVC (Actual) | Timeliness (All) | All) | Actual) |  |  | SOP to fill CW1 fields are not followed by Operators due to lack of resources
53 | SC3 – S50 | Received origin CFS (Actual) | Completeness (All) | All) | Actual) |  |  | Manual milestones not updated on time by Operators due to lack of resources
54 | SC3 – S50 | Received origin CFS (Actual) | Timeliness (All) | All) | Actual) |  |  | Manual milestones not updated on time by Operators due to lack of resources
55 | SC3 – S53 | Full Container loaded on vessel (Actual) | Completeness (All) | All) | Actual) |  |  | CW1 configurations are not set up correctly to handle Bosch requirements
56 | SC3 – S53 | Full Container loaded on vessel (Actual) | Timeliness (All) | All) | Actual) |  |  | CW1 configurations are not set up correctly to handle Bosch requirements
57 | SC3 – S04 | Vessel/flight departed (Actual) | Completeness (Critical) | Critical) | Actual) |  |  | The Consol is not attached to shipment with "is Linked" Flag
58 | SC3 – S04 | Vessel/flight departed (Actual) | Timeliness (Critical) | Critical) | Actual) |  |  | The Consol is not attached to shipment with "is Linked" Flag
59 | SC3 – S04 | Vessel/flight departed (Estimated) | Completeness (Critical) | Critical) | Estimated) |  |  | The Consol is not attached to shipment with "is Linked" Flag
60 | SC3 – S04 | Vessel/flight departed (Estimated) | Timeliness (Critical) | Critical) | Estimated) |  |  | The Consol is not attached to shipment with "is Linked" Flag
61 | SC3 – S07 | Vessel/flight arrived (Actual) | Completeness (Critical) | Critical) | Actual) |  |  | The Consol is not attached to shipment with "is Linked" Flag
62 | SC3 – S07 | Vessel/flight arrived (Actual) | Timeliness (Critical) | Critical) | Actual) |  |  | The Consol is not attached to shipment with "is Linked" Flag
63 | SC3 – S07 | Vessel/flight arrived (Estimated) | Completeness (Critical) | Critical) | Estimated) |  |  | The Consol is not attached to shipment with "is Linked" Flag
64 | SC3 – S07 | Vessel/flight arrived (Estimated) | Timeliness (Critical) | Critical) | Estimated) |  |  | The Consol is not attached to shipment with "is Linked" Flag
65 | SC3 – S54 | Full Container discharge (Actual) | Completeness (All) | All) | Actual) |  |  | CW1 configurations are not set up correctly to handle Bosch requirements
66 | SC3 – S54 | Full Container discharge (Actual) | Timeliness (All) | All) | Actual) |  |  | CW1 configurations are not set up correctly to handle Bosch requirements
67 | SC3 – S51 | Arrived destination CFS (Actual) | Completeness (All) | All) | Actual) |  |  | CW1 configurations are not set up correctly to handle Bosch requirements
68 | SC3 – S51 | Arrived destination CFS (Actual) | Timeliness (All) | All) | Actual) |  |  | CW1 configurations are not set up correctly to handle Bosch requirements
69 | SC3 – S13 | On hand at destination SVC (Actual) | Completeness (All) | All) | Actual) |  |  | Manual milestones not updated on time by Operators due to lack of resources
70 | SC3 – S13 | On hand at destination SVC (Actual) | Timeliness (All) | All) | Actual) |  |  | Manual milestones not updated on time by Operators due to lack of resources
71 | SC3 – S45 | Handover to broker (Actual) | Completeness (Critical) | Critical) | Actual) |  |  | The HBL div mode is changed after receiving
72 | SC3 – S45 | Handover to broker (Actual) | Timeliness (Critical) | Critical) | Actual) |  |  | The HBL div mode is changed after receiving
73 | SC3 – S45 | Handover to broker (Estimated) | Completeness (Critical) | Critical) | Estimated) |  |  | The HBL div mode is changed after receiving
74 | SC3 – S45 | Handover to broker (Estimated) | Timeliness (Critical) | Critical) | Estimated) |  |  | The HBL div mode is changed after receiving
75 | SC3 – S05 | In delivery (Actual) | Completeness (All) | All) | Actual) |  |  | Milestone is dependent on Manual input and is missed due to Lack of resources
76 | SC3 – S05 | In delivery (Actual) | Timeliness (All) | All) | Actual) |  |  | Milestone is dependent on Manual input and is missed due to Lack of resources
77 | SC3 – S31 | Delivered (Actual) | Completeness (Critical) | Critical) | Actual) |  |  | Milestone is dependent on Manual input and is missed due to Lack of resources
78 | SC3 – S31 | Delivered (Actual) | Timeliness (Critical) | Critical) | Actual) |  |  | Milestone is dependent on Manual input and is missed due to Lack of resources
79 | SC3 – S31 | Delivered (Estimated) | Completeness (Critical) | Critical) | Estimated) |  |  | Milestone is dependent on Manual input and is missed due to Lack of resources
80 | SC3 – S31 | Delivered (Estimated) | Timeliness (Critical) | Critical) | Estimated) |  |  | Milestone is dependent on Manual input and is missed due to Lack of resources
81 | SC3 – S55 | Empty Container returned (Actual) | Completeness (All) | All) | Actual) |  |  | Milestone is dependent on Manual input and is missed due to Lack of resources
82 | SC3 – S55 | Empty Container returned (Actual) | Timeliness (All) | All) | Actual) |  |  | Milestone is dependent on Manual input and is missed due to Lack of resources
83 | SC4 – S07 | For "to Port" Shipments, milestone estimates are not received 7 days before of the actual Milestone event | ETA accuracy 2P |  |  | Estimates are not received 7 days before of the Actual event |  | CW1 lacks chronological sequence validation
84 | SC3 – S07 | For "to Port" Shipments, milestone estimates are not received 7 days before of the actual Milestone event | ETA accuracy 2P |  |  | Estimates are not received 7 days before of the Actual event |  | CW1 lacks chronological sequence validation
85 | SC4 – S31 | For "to Door" Shipments, milestone estimates are not received 7 days before of the actual Milestone event | ETA accuracy 2D |  |  | Estimates are not received 7 days before of the Actual event |  | CW1 lacks chronological sequence validation
86 | SC3 – S31 | For "to Door" Shipments, milestone estimates are not received 7 days before of the actual Milestone event | ETA accuracy 2D |  |  | Estimates are not received 7 days before of the Actual event |  | CW1 lacks chronological sequence validation
87 | SC4 - <Origin> | Shipment received by Bosch doesn't have the CIV or DN reference |  |  |  | Shipment received by Bosch doesn't have the CIV or DN reference |  | The refrences are not updated from CIV or PKL docs
88 | SC4 - <Origin> | Shipment received by Bosch has the CIV or DN reference but do not have the correct data |  |  |  | Shipment received by Bosch has the CIV or DN reference but do not have the correct data |  | The refrences are not updated from CIV or PKL docs

## Rootcauses
Num | Rootcause | counter measure | Measure 1 | Measure 2 | Measure 3
1 | SOP to fill CW1 fields are not followed by Operators due to lack of resources | add FTEs | Dedicated Ops owner is 3 most afftected Regions (GCA + NEC + CSE) to focus on completness of Manual milestones S02, S31, S00 | Ops retraining in Problemetic area | Dedicated Ops owner is 3 most afftected Regions (GCA + NEC + CSE) to focus on Timeliness of Manual milestones S02, S31, S00
2 | CW1 configurations are not set up correctly to handle Bosch requirements | Tech workflow | Implement Mandatory Field Validation in CW1 , causing EDI faliure | Review the legacy system shipments flow for the branch in Japan | Review the legacy system shipments flow for the branch in Japan
3 | CW1 lacks chronological sequence validation | Tech workflow | Implement date sequence field validation in CW1 for Milestone | Optmise automation flow of ETD / ETA Milestones in operation system (CW1) | Add Plausibility Measures into the Control Tower Dashboard
4 | The Consol is not attached to shipment with "is Linked" Flag |  | Optimise automation flow of ETD / ETA Milestones in operation system (CW1)
5 | The HBL div mode is changed after receiving |  | TS to review and address the data fields completition across Maersk systems (CW1, ALP, Seeburger) causing failures in the EDI delivery of critical milestones to Bosch system | Fix S45 trigger based on the HBL div mode
6 | The refrences are not updated from CIV or PKL docs |  | Review Feasibility of Compliance AI Tool Matching Invoice & Delivery Note Numbers | Ops retraining in Problemetic area | Ramp up SC3 Volume from 40% to 80%
7 | Manual milestones not updated on time by Operators due to lack of resources | add FTEs | Dedicated Ops owner is 3 most afftected Regions (GCA + NEC + CSE) to focus on completness of Manual milestones S02, S31, S00 | Dedicated Ops owner is 3 most afftected Regions (GCA + NEC + CSE) to focus on Timeliness of Manual milestones S02, S31, S00
8 | The Estimate updated too late in the lifecycle |  | Optimise automation flow of ETD / ETA Milestones in operation system (CW1) | Ops retraining in Problemetic area
9 | Milestone is dependent on Manual input and is missed due to Lack of resources | add FTEs | Dedicated Ops owner is 3 most afftected Regions (GCA + NEC + CSE) to focus on completness of Manual milestones S02, S31, S00 | Dedicated Ops owner is 3 most afftected Regions (GCA + NEC + CSE) to focus on Timeliness of Manual milestones S02, S31, S00
10 | The Automation of the Milestones is not working based the DEX events | Tech workflow | Retrigger missing Milestones for delivered Shipments
11 | Ops discipline in updating refrences in MY, TH |  | Ops retraining in Problemetic area
12
13
14
15
16
17
18
19
20

## Measures
Nr. | Measures | Category | Responsible | Link to RootCause
1 | TS to review and address the data fields completition across Maersk systems (CW1, ALP, Seeburger) causing failures in the EDI delivery of critical milestones to Bosch system | Completeness | Maersk ( Akhil)
2 | TS to review and address the data fields completition across Maersk systems (CW1, ALP, Seeburger) causing failures in the EDI delivery of critical milestones to Bosch system | Timeliness | Maersk ( Akhil)
3 | Optmise automation flow of ETD / ETA Milestones in operation system (CW1) | ETA accuracy 2P | Maersk (Timmy)
4 | Ramp up SC3 Volume from 40% to 80% | Completeness (All) | Bosch
5 | Ramp up SC3 Volume from 40% to 80% | Timeliness (All) | Bosch
6 | Ramp up SC3 Volume from 40% to 80% | Reference Quality | Bosch
7 | Optimise automation flow of ETD / ETA Milestones in operation system (CW1) | ETA accuracy 2D | Maersk (Timmy)
8 | Implement Mandatory Field Validation in CW1 , causing EDI faliure | Timeliness | Maersk (Timmy)
9 | Review Feasibility of Compliance AI Tool Matching Invoice & Delivery Note Numbers | Reference Quality | Maersk (Harsh)
10 | Review the legacy system shipments flow for the branch in Japan | Completeness | Maersk ( Josh)
11 | Review the legacy system shipments flow for the branch in Japan | Timeliness | Maersk ( Josh)
12 | Add Plausibility Measures into the Control Tower Dashboard | Plausability | MAersk ( Jacob)
13 | Implement date sequence field validation in CW1 for Milestone | Plausability | Maersk (Timmy)
14 | Retrigger missing Milestones for delivered Shipments | Completeness | Maersk ( Alberto)
15 | Dedicated Ops owner is 3 most afftected Regions (GCA + NEC + CSE) to focus on completness of Manual milestones S02, S31, S00 | Completeness | Maersk (Ops)
16 | Dedicated Ops owner is 3 most afftected Regions (GCA + NEC + CSE) to focus on Timeliness of Manual milestones S02, S31, S00 | Timeliness | Maersk (Ops)
17 | Ops retraining in Problemetic area | Reference Quality | Maersk (Ops)
18 | Fix S45 trigger based on the HBL div mode | Completeness (All) | Maersk (Timmy)
Note on C1: Dudek Jaroslaw (GS/PSD32): MRC Managerial Root Caus TRC Technical Root Cause Bug-Fix Others

## Current State
MAERSK Milestone Performance - Current State Analysis
Overall Performance Summary
Metric | Current | Target | Gap
Total Status Codes Required | 43415 | 43415 | 0
Overall Completion Rate | 66.5% | 95% | 28.5%
Overall Timeliness Rate | 41.21% | 95% | 53.79%
Milestone Performance Details
Milestone | Required | Available | In Time | Completion % | Timeliness % | Completion Gap | Timeliness Gap | Total Impact | Cumulative %
S02 - Collected | 5502 | 4621 | 1140 | 83.99% | 20.72% | 11.01% | 74.28% | 4692.8 | 13.1%
S31 - Delivered | 4464 | 3387 | 1761 | 75.87% | 39.45% | 19.13% | 55.55% | 3333.6 | 22.5%
S13 - On hand at destination SVC | 1779 | 139 | 89 | 7.813% | 5.003% | 87.19% | 90% | 3152.1 | 31.3%
S05 - In delivery | 2232 | 686 | 542 | 30.73% | 24.28% | 64.27% | 70.72% | 3012.8 | 39.7%
S07 - Vessel/ flight arrived | 6636 | 5890 | 4338 | 88.76% | 65.37% | 6.242% | 29.63% | 2380.4 | 46.4%
S04 - Vessel/ flight departed | 6636 | 6029 | 4326 | 90.85% | 65.19% | 4.147% | 29.81% | 2253.4 | 52.7%
S51 - Arrived destination CFS | 1539 | 479 | 322 | 31.12% | 20.92% | 63.88% | 74.08% | 2123.1 | 58.6%
S46 - Documents rcvd from shipper | 1372 | 427 | 179 | 31.12% | 13.05% | 63.88% | 81.95% | 2000.8 | 64.2%
S00 - Shipment created | 1372 | 412 | 406 | 30.03% | 29.59% | 64.97% | 65.41% | 1788.8 | 69.2%
S17 - Tendered carrier | 1200 | 419 | 204 | 34.92% | 17% | 60.08% | 78% | 1657 | 73.9%
S11 - On hand at origin Hub/ CC | 1200 | 433 | 297 | 36.08% | 24.75% | 58.92% | 70.25% | 1550 | 78.2%
S16 - Shipment booked with carrier | 1372 | 715 | 551 | 52.11% | 40.16% | 42.89% | 54.84% | 1340.8 | 82%
S45 - Handover to broker | 1594 | 954 | 840 | 59.85% | 52.7% | 35.15% | 42.3% | 1234.6 | 85.4%
S18 - Recovered from carrier | 621 | 40 | 15 | 6.441% | 2.415% | 88.56% | 92.58% | 1124.9 | 88.6%
S12 - On hand at destination Hub/ CC | 621 | 167 | 46 | 26.89% | 7.407% | 68.11% | 87.59% | 966.9 | 91.3%
S10 - On hand at origin SVC | 2358 | 2181 | 1437 | 92.49% | 60.94% | 2.506% | 34.06% | 862.2 | 93.7%
S50 - Received origin CFS | 1539 | 1275 | 841 | 82.85% | 54.65% | 12.15% | 40.35% | 808.1 | 96%
S54 - Full Container discharge from vessel | 285 | 33 | 30 | 11.58% | 10.53% | 83.42% | 84.47% | 478.5 | 97.3%
S52 - Empty Container picked up | 250 | 76 | 53 | 30.4% | 21.2% | 64.6% | 73.8% | 346 | 98.3%
S53 - Full Container loaded on vessel | 285 | 129 | 119 | 45.26% | 41.75% | 49.74% | 53.25% | 293.5 | 99.1%
S55 - Empty Container returned | 275 | 124 | 113 | 45.09% | 41.09% | 49.91% | 53.91% | 285.5 | 99.9%
S60 - Pre-Booking confirmed | 281 | 252 | 241 | 89.68% | 85.77% | 5.32% | 9.235% | 40.9 | 100%
S61 - Pre-Booking declined | 2 | 2 | 0 | 100% | 0% | -5% | 95% | 1.8 | 100%

## Pareto Analysis
Pareto Analysis - 80/20 Impact
Key Insight: Top 11 milestones (48% of total) contribute 80% of the performance impact
Rank | Milestone | Total Impact | Cumulative Impact | Cumulative %
1 | S02 - Collected | 4692.8 | 4692.8 | 13.1% | Critical
2 | S31 - Delivered | 3333.6 | 8026.4 | 22.5% | Critical
3 | S13 - On hand at destination SVC | 3152.1 | 11178.5 | 31.3%
4 | S05 - In delivery | 3012.8 | 14191.3 | 39.7% | Container Level
5 | S07 - Vessel/ flight arrived | 2380.4 | 16571.7 | 46.4% | Critical
6 | S04 - Vessel/ flight departed | 2253.4 | 18825.1 | 52.7% | Critical
7 | S51 - Arrived destination CFS | 2123.1 | 20948.2 | 58.6% | Container Level
8 | S46 - Documents rcvd from shipper | 2000.8 | 22949 | 64.2%
9 | S00 - Shipment created | 1788.8 | 24737.8 | 69.2% | Critical
10 | S17 - Tendered carrier | 1657 | 26394.8 | 73.9% | Container Level
11 | S11 - On hand at origin Hub/ CC | 1550 | 27944.8 | 78.2%
12 | S16 - Shipment booked with carrier | 1340.8 | 29285.6 | 82%
13 | S45 - Handover to broker | 1234.6 | 30520.2 | 85.4%
14 | S18 - Recovered from carrier | 1124.9 | 31645.1 | 88.6%
15 | S12 - On hand at destination Hub/ CC | 966.9 | 32612 | 91.3%
16 | S10 - On hand at origin SVC | 862.2 | 33474.2 | 93.7%
17 | S50 - Received origin CFS | 808.1 | 34282.3 | 96%
18 | S54 - Full Container discharge from vessel | 478.5 | 34760.8 | 97.3%
19 | S52 - Empty Container picked up | 346 | 35106.8 | 98.3%
20 | S53 - Full Container loaded on vessel | 293.5 | 35400.3 | 99.1%
21 | S55 - Empty Container returned | 285.5 | 35685.8 | 99.9%
22 | S60 - Pre-Booking confirmed | 40.9 | 35726.7 | 100%
23 | S61 - Pre-Booking declined | 1.8 | 35728.5 | 100%

## Regional actions
Region | Action Item | Metrics | Priority | Owner | Name | ETA | Status
EUR | Check and confirm resourcing and FTE capacity to reach target by end April for the 3 areas: NEC, EME and CSE | Missing Milestones | P0 | Area and Region LCL Ops leader | Christine Kühl | 2026-02-05 | Completed, all areas confirmed capacity needs and approvals needed.
APA | Check and confirm resourcing and FTE capacity to reach target by end April for the 3 areas: GCA, SEA, MEK |  | P0 | Area and Region LCL Ops leader | Jos Raaymakers | 2026-02-05 | SEA confirmed capacity. GCA to confirm back by 06-Feb.
EUR | Improve reporting quality of milestone completeness (with filters) to enable operations to be proactive. |  | P0 | Central reporting team | Christine Kühl | 2026-02-09 | Daily reporting to be enhanced for ops to be more proactive. Call on Monday to be followed by report refining.
GCA | Conduct root cause analysis for 1195 missing milestones | Missing Milestones | P0 | Regional Ops Lead | Jos Raaymakers | 2026-02-01 | In Progress
GCA | Implement mandatory field validation at booking for 1446 milestones | Missing Mandatory | P0 | Regional Ops Lead | Jos Raaymakers | 2026-02-01 | Not Started
CSE | Reverse declining trend (661→701) milestones missing - Stop the bleeding | Missing Milestones | P0 | Regional Ops Lead | Christine Kühl | 2026-02-01 | Not Started
CSE | Fix 1521 missing mandatory information fields | Missing Mandatory | P0 | Regional Ops Lead | Christine Kühl | 2026-02-01 | Not Started
NEC | Continue improvement trend (892→753) - Accelerate | Missing Milestones | P0 | Regional Ops Lead | Christine Kühl | 2026-02-01
NEC | Address 2676 mandatory info gaps (highest volume) | Missing Mandatory | P0 | Data Quality Team | Christine Kühl | 2026-02-01 | Not Started
EME | Sustain improvement | Missing Milestones | P1 | Regional Ops Lead | Christine Kühl | 2026-02-01 | In Progress
EME | Focus on Mandatory Fields missing (198) | Missing Mandatory | P1 | Regional Ops Lead | Christine Kühl | 2026-02-01 | In Progress
SEA | Reduce 275 missing milestones through standardization | Missing Milestones | P1 | Regional Ops Lead | Jos Raaymakers | 2026-02-01 | In Progress
SEA | Focus on Mandatory Fields (303) | Missing Mandatory |  |  | Jos Raaymakers | 2026-02-01
MEK | Maintain strong performance (121 missing) - Monitor | Missing Milestones | P2 | Regional Ops Lead | Jos Raaymakers | 2026-02-01 | In Progress
NEA | Slight improvement opportunity (151→<100) | Missing Milestones | P2 | Regional Ops Lead | Jos Raaymakers | 2026-02-01 | Not Started

## Targets
Metrics name | 2025.11 | 2025.12 |  | Week 4 | 2026.04 Target | 2026.04 Target
|  |  | Week 1-3 |  | (Maersk proposal) | (Bosch proposal) | Comments
Milestone Completeness ( S02,S04,S07,S31) | 82% | 84% | 85.8% | 86.5% | 95% | 95% | ✅ ACHIEVABLE : - Fix top 3 Missing fields in CW1 (Process/Tech) - Path toward 80% SC3 booking (Bosch) - Sustainable fix by stricter validation in Workflows (Process/Tech)
Milestone Timeliness ( S02,S04,S07,S31) | 10% | 22% | 48.6% | 45.5% | ?? | 95% | ⚠️ STRETCH and EDI DEPENDENT: - 85% ONLY achievable at 80% SC3 (Bosch) - With Dedicated Control tower and proactive update we can hit Close to 60% (Operations)
Milestone Completeness ( All) | Not Measured | Not Measured | 85.8% | 86.5% | 90% | 95% | ✅ ACHIEVABLE - Fix top 3 Missing fields in CW1 yields 18,6 % increase - Can be achieved with due diligance from CT on proactively updating missing fields (Operations)
Milestone Timeliness (All) | Not Measured | Not Measured | 48.6% | 45.5% | ?? | 95% | ⚠️ EDI DEPENDENT - The timeliness metrics can't be met with current EDI ratio, SC3 booking needs to be at ~75% to hit 80 % timeliness or ~80% to achieve 85% timeliness
SC4 Refrence Completeness |  |  | 65% | 65% | ?? | 95% | -DN OR CIV Number at 91 % for Field present. But filtering out for Junk value it stands at 80 %; - Conversion of SC4 --> SC3 will drastically improve accuracy Data to be verifiied on wrong refrence by end of next week - Shared by Bosch on Wednesday EOD
ETA accuracy/reliability 2P shipments |  |  |  | 1.5% |  | 95% | Data to be analyzed by next week
ETA accuracy/reliability 2D shipments |  |  |  | 33% |  | 95% | Data to be analyzed by next week

## ETA accuracy Port
Port Shipment ETA Accuracy — January 2026 ARR
1235 Housebills with ARR in January 2026 ¦ Dual-view: ≥7 Day Lead Time vs Any Lead Time
VIEW 1: ETA Published ≥7 Days Before ARR |  |  |  | VIEW 2: Latest ETA (Any Lead Time)
Total Jan HBs | With ≥7d ETA | ETA <7d only | No ETA | Total Jan HBs | With ETA | Missing ETA | Median Dev
1235 | 65 | 1165 | 5 | 1235 | 1175 | 5 | 1.2h
Of the 65 with ≥7d ETA: |  |  |  | Of the 1175 with any ETA:
Within ±48h | 19 | 29.2% |  | Within ±48h | 1091 | 92.9%
Late (ARR after ETA) | 39 | 60.0% |  | Late (ARR after ETA) | 77 | 6.6%
Early (ARR before ETA) | 7 | 10.8% |  | Early (ARR before ETA) | 7 | 0.6%
≥7d Accuracy (of matched): 19/65 = 29.2% |  |  |  | Any-lead Accuracy (of matched): 1091/1175 = 92.9%
≥7d Accuracy (overall): 19/1235 = 1.5% |  |  |  | Any-lead Accuracy (overall): 1091/1235 = 88.3%
Median deviation: 50.2h ¦ Mean: 75.8h
Category | Count |  |  | Category | Count
Within ±48h | 19 |  |  | Within ±48h | 1091
Late | 39 |  |  | Late | 77
Early | 7 |  |  | Early | 7
ETA <7d (no qualifying) | 1165 |  |  | Missing ETA | 5
No ETA | 5

## POD estimate Accuracy
Door Shipment POD Accuracy — Dual View Analysis
2642 Housebills with actual POD ¦ POD_ estimate accuracy at ≥7 Day vs Any Lead Time
VIEW 1: POD_ Published ≥7 Days Before POD |  |  |  | VIEW 2: Latest POD_ (Any Lead Time)
Total HBs | With ≥7d POD_ | POD_ <7d only | No POD_ | Total HBs | With POD_ | Missing POD_ | Median Dev
2642 | 2520 | 120 | 2 | 2642 | 2570 | 2 | 1.7h
Of the 2520 with ≥7d POD_: |  |  |  | Of the 2570 with any POD_:
Within ±48h | 840 | 33.3% |  | Within ±48h | 1520 | 59.1%
Late | 1617 | 64.2% |  | Late | 1003 | 39.0%
Early | 63 | 2.5% |  | Early | 47 | 1.8%
≥7d Accuracy (of matched): 840/2520 = 33.3% |  |  |  | Any-lead Accuracy (matched): 1520/2570 = 59.1%
≥7d Accuracy (overall): 840/2642 = 31.8% |  |  |  | Any-lead Accuracy (overall): 1520/2642 = 57.5%
Median deviation: 209.3h ¦ Mean: 848.8h |  |  |  | Retroactive POD_ (published after POD): 701 HBs excluded
Category | Count |  |  | Category | Count
Within ±48h | 840 |  |  | Within ±48h | 1520
Late | 1617 |  |  | Late | 1003
Early | 63 |  |  | Early | 47
POD_ <7d | 120 |  |  | Missing POD_ | 2
No POD_ | 2

## Evidence - Reference
Reference Completeness — Breakdown by Origin Country
▸ All Weeks Aggregate (CW01–CW07, min. 5 shipments)
Country Code | Country Name | Shipments | Ref Complete (%) | Gap Rate (%) | CIV Rate (%) | DN Rate (%) | Both CIV+DN (%) | Status
MY | Malaysia | 115 | 0% | 100% | 0% | 0% | 0% | 🔴 Critical
TH | Thailand | 125 | 0.8% | 99.2% | 0% | 0.8% | 0% | 🔴 Critical
PL | Poland | 18 | 5.556% | 94.44% | 5.556% | 5.556% | 5.556% | 🔴 Critical
FR | France | 20 | 10% | 90% | 0% | 10% | 0% | 🔴 Critical
BE | BE | 8 | 12.5% | 87.5% | 0% | 12.5% | 0% | 🔴 Critical
RO | Romania | 24 | 20.83% | 79.17% | 16.67% | 4.167% | 0% | 🔴 Critical
GB | GB | 5 | 40% | 60% | 20% | 40% | 20% | 🟠 High
ES | Spain | 34 | 41.18% | 58.82% | 26.47% | 29.41% | 14.71% | 🟠 High
SG | Singapore | 22 | 45.45% | 54.55% | 0% | 45.45% | 0% | 🟠 High
NL | Netherlands | 13 | 46.15% | 53.85% | 0% | 46.15% | 0% | 🟠 High
JP | Japan | 232 | 52.16% | 47.84% | 48.28% | 7.759% | 3.879% | 🟠 High
KR | South Korea | 51 | 54.9% | 45.1% | 52.94% | 1.961% | 0% | 🟠 High
PT | Portugal | 21 | 57.14% | 42.86% | 52.38% | 9.524% | 4.762% | 🟠 High
TR | Turkey | 12 | 58.33% | 41.67% | 33.33% | 58.33% | 33.33% | 🟠 High
IT | Italy | 86 | 63.95% | 36.05% | 62.79% | 6.977% | 5.814% | 🟡 Medium
VN | Vietnam | 43 | 72.09% | 27.91% | 72.09% | 0% | 0% | 🟡 Medium
CH | Switzerland | 35 | 74.29% | 25.71% | 5.714% | 74.29% | 5.714% | 🟡 Medium
CN | China | 1649 | 76.05% | 23.95% | 74.17% | 13.95% | 12.07% | 🟡 Medium
TW | Taiwan | 98 | 78.57% | 21.43% | 78.57% | 8.163% | 8.163% | 🟡 Medium
AT | Austria | 5 | 80% | 20% | 80% | 80% | 80% | 🟡 Medium
HU | Hungary | 21 | 80.95% | 19.05% | 76.19% | 14.29% | 9.524% | 🟢 Low
SK | Slovakia | 19 | 84.21% | 15.79% | 26.32% | 84.21% | 26.32% | 🟢 Low
HK | Hong Kong | 269 | 85.5% | 14.5% | 83.27% | 3.346% | 1.115% | 🟢 Low
SE | Sweden | 14 | 85.71% | 14.29% | 0% | 85.71% | 0% | 🟢 Low
CZ | Czech Rep. | 56 | 85.71% | 14.29% | 46.43% | 75% | 35.71% | 🟢 Low
DE | Germany | 825 | 89.09% | 10.91% | 79.52% | 81.21% | 71.64% | 🟢 Low
BA | BA | 5 | 100% | 0% | 100% | 100% | 100% | 🟢 Low
SI | SI | 8 | 100% | 0% | 87.5% | 37.5% | 25% | 🟢 Low

## Evidence - Sync & Plausibility
SYNC, DTL & PLAUSIBILITY — Deep Analysis (16-Feb)
THREE-SOURCE SYNC: ROOT CAUSE (from 16-Feb meeting)
CargoWise → Track & Trace Excel: SAME data, full operational extract
CargoWise → Maersk.com: Generic/public subset (standard offering only)
CargoWise → Seeburger DTL → EDI to Bosch: Quality checks FILTER messages
ROOT CAUSE: When DTL checks fail → message blocked → Bosch sees 'missing milestone'
Error log exists internally but no structured feedback loop to operations
PDCA REQUIRED: Document DTL checks, establish ops feedback loop, log monitoring
SC3/SC4 DOUBLE BOOKING (NEW from meeting)
~1/3 of shipments labeled SC4 were actually received as SC3
Cause: Incomplete SC3 → operator follows up via email → converts to SC4
Bosch suppliers also send emails when SC3 exists → creates duplicates
Fix (Maersk): Eurolog S09 + reason O01 to close duplicates (Karina)
Fix (Bosch): Instruct suppliers to stop emails when SC3 exists
MILESTONE INCONSISTENCY — DEEP ANALYSIS (662 Shipments, 1,500 Records)
Metric | Value | Significance
Total records in dataset | 1,500 | Across ETA (1,000) and ATA (500) violations
Unique affected HBLs | 550 of 662 (83%) | Vast majority of flagged shipments have real issues
ETA sequence violations | 475 unique HBLs | Estimates with impossible date order
ATA sequence violations | 76 unique HBLs | ACTUALS recorded in wrong order — data quality failure
Dominant issue | POD > Delivery (83%) | Port arrival dated after door delivery — physically impossible
NON TMC / SC4 share | 63% of ETA violations | Manual entry is the primary root cause (300 HBLs)
61-90 day gap cluster | 31% of POD>Delivery | Suggests bulk upload / template error pattern
ATA median gap | 73 days | Actuals MORE wrong than estimates — operators entering out-of-sequence
ETA median gap | 15 days | Estimates are wrong but less severely than actuals
DUPLICATION CLARIFICATION:
Multiple ETA rows per HBL = VALID (estimates get revised; 51% of HBLs have 2+ revisions)
ATA rows: duplicated with IDENTICAL dates (multiple containers/TOs per shipment)
No conflicting actual dates found — ATA duplication is structural, not a data quality issue
The 76 ATA violations are genuine sequence errors, not duplication artifacts
POD > DELIVERY GAP SEVERITY (1,010 records — 83% of all violations)
Bucket | ETA Records | ATA Records | % of Total | Likely Cause
1-7 days | 309 | 52 | 35.7% | Timezone / rounding — low severity but still invalid
8-30 days | 171 | 28 | 19.7% | Operator error — medium severity
31-60 days | 99 | 13 | 11.1% | Wrong milestone updated — high severity
61-90 days | 278 | 32 | 30.7% | Bulk upload / template error — SYSTEMIC pattern
>90 days | 22 | 6 | 2.8% | Data corruption — critical (up to 367 days)
PROPOSED PLAUSIBILITY RULES (for dashboard — committed Nov '25, OVERDUE)
Rule | Condition | Severity | Auto-Action | Expected Catch
Seq: POD > Delivery | Port Discharge after Door Delivery | Critical | Block + alert | 83% of violations
Seq: POL > POD | Vessel departure after port arrival | Critical | Block + alert | 4% of violations
Seq: Pickup > POL | Collection after vessel departure | Critical | Block + alert | 8% of violations
Gap: >60d between stages | Unrealistic transit gap | Warning | Flag for review | 31% severity bucket
ATA gap > 73d | Actuals with extreme gaps | Critical | Lock record | 76 ATA HBLs
Retroactive: ETA after ATA | Estimate updated after actual | Critical | Prevent edit | 701+ HBLs (POD data)
Bulk: >50 same-day edits | Mass update pattern detection | Warning | Flag batch | Dec 12: 994 HBLs
ESCALATION: Dashboard + rules committed Nov '25. Mimel aware. Must show progress Thursday 19-Feb.

## SC4 Trend
SC4 - Week-over-Week Trend Summary
CRITICAL MILESTONES (S00, S02, S04, S07, S31, S45)
Milestone | Type | Metric | Week 1 | Week 2 | Week 3 | Week 4 | W1→W4 Delta
S00 - Shipment created | Actual | Completeness | 52% | 36% | 35% | 50% | -2%
S00 - Shipment created | Actual | Timeliness | 52% | 36% | 35% | 49% | -3%
S02 - Collected | Estimated | Completeness | 79% | 83% | 85% | 87% | 8%
S02 - Collected | Estimated | Timeliness | 41% | 36% | 34% | 43% | 2%
S02 - Collected | Actual | Completeness | 92% | 95% | 88% | 90% | -2%
S02 - Collected | Actual | Timeliness | 17% | 39% | 34% | 40% | 23%
S04 - Vessel/ flight departed | Estimated | Completeness | 99% | 99% | 96% | 97% | -2%
S04 - Vessel/ flight departed | Estimated | Timeliness | 38% | 43% | 37% | 43% | 5%
S04 - Vessel/ flight departed | Actual | Completeness | 96% | 93% | 83% | 88% | -8%
S04 - Vessel/ flight departed | Actual | Timeliness | 83% | 55% | 52% | 54% | -29%
S07 - Vessel/ flight arrived | Estimated | Completeness | 100% | 96% | 93% | 94% | -6%
S07 - Vessel/ flight arrived | Estimated | Timeliness | 26% | 21% | 18% | 22% | -4%
S07 - Vessel/ flight arrived | Actual | Completeness | 83% | 83% | 81% | 84% | 1%
S07 - Vessel/ flight arrived | Actual | Timeliness | 33% | 66% | 61% | 52% | 19%
S45 - Handover to broker | Actual | Completeness | 100% | 100% | 56% | 42% | -58%
S45 - Handover to broker | Actual | Timeliness | 100% | 92% | 54% | 37% | -63%
S31 - Delivered | Estimated | Completeness | 96% | 99% | 97% | 98% | 2%
S31 - Delivered | Estimated | Timeliness | 80% | 82% | 70% | 67% | -13%
S31 - Delivered | Actual | Completeness | 100% | 100% | 76% | 83% | -17%
S31 - Delivered | Actual | Timeliness | 4% | 12% | 29% | 9% | 5%
Critical Milestone Averages
|  | Avg Completeness | 89.7% | 88.4% | 79% | 81.3% | -8.4%
|  | Avg Timeliness | 47.4% | 48.2% | 42.4% | 41.6% | -5.8%
ALL MILESTONES - AVERAGES
|  | Metric | Week 1 | Week 2 | Week 3 | Week 4 | W1→W4 Delta
|  | Avg Completeness | 72.24% | 64.67% | 61.62% | 70.81% | -1.429%
|  | Avg Timeliness | 39.24% | 37.38% | 33.43% | 38.71% | -0.5238%

## SC3 Trend
SC3 - Week-over-Week Trend Summary
CRITICAL MILESTONES (S02, S04, S07, S31, S45)
Milestone | Type | Metric | Week 1 | Week 2 | Week 3 | Week 4 | W1→W4 Delta
S02 - Collected | Actual | Completeness | 81.3% | 79.2% | 73% | 79.1% | -2.2%
S02 - Collected | Actual | Timeliness | 31.7% | 39.2% | 31.8% | 31.7% | 0%
S02 - Collected | Estimated | Completeness | 81.3% | 80.9% | 77.7% | 83.9% | 2.6%
S02 - Collected | Estimated | Timeliness | 0% | 0% | 0% | 0% | 0%
S04 - Vessel/ flight departed | Actual | Completeness | 86.6% | 86.4% | 84.3% | 80.1% | -6.5%
S04 - Vessel/ flight departed | Actual | Timeliness | 85.8% | 85.8% | 81.7% | 78.1% | -7.7%
S04 - Vessel/ flight departed | Estimated | Completeness | 86.6% | 89.5% | 86.3% | 84.6% | -2%
S04 - Vessel/ flight departed | Estimated | Timeliness | 68.8% | 72.4% | 70.6% | 68.1% | -0.7%
S07 - Vessel/ flight arrived | Actual | Completeness | 90.5% | 90.1% | 86.3% | 86% | -4.5%
S07 - Vessel/ flight arrived | Actual | Timeliness | 88.5% | 88.9% | 85% | 84.9% | -3.6%
S07 - Vessel/ flight arrived | Estimated | Completeness | 88.1% | 91.3% | 87.9% | 86.6% | -1.5%
S07 - Vessel/ flight arrived | Estimated | Timeliness | 83.4% | 86.4% | 83% | 82.6% | -0.8%
S45 - Handover to broker | Actual | Completeness | 36.9% | 27.9% | 40.6% | 46.8% | 9.9%
S45 - Handover to broker | Actual | Timeliness | 36.9% | 27.9% | 39.6% | 45.2% | 8.3%
S45 - Handover to broker | Estimated | Completeness | 9.1% | 25% | 37.5% | 51.4% | 42.3%
S45 - Handover to broker | Estimated | Timeliness | 9.1% | 25% | 37.5% | 45.9% | 36.8%
S31 - Delivered | Actual | Completeness | 42.2% | 57.5% | 54% | 58.3% | 16.1%
S31 - Delivered | Actual | Timeliness | 14.4% | 15.4% | 10.1% | 9.4% | -5%
S31 - Delivered | Estimated | Completeness | 72.2% | 76.4% | 69.4% | 70.9% | -1.3%
S31 - Delivered | Estimated | Timeliness | 57.8% | 58.7% | 50.4% | 46.8% | -11%
Critical Milestone Averages
|  | Avg Completeness | 67.48% | 70.42% | 69.7% | 72.77% | 5.29%
|  | Avg Timeliness | 47.64% | 49.97% | 48.97% | 49.27% | 1.63%
ALL MILESTONES - AVERAGES
|  | Metric | Week 1 | Week 2 | Week 3 | Week 4 | W1→W4 Delta
|  | Avg Completeness | 57.38% | 61.62% | 60.98% | 63.02% | 5.64%
|  | Avg Timeliness | 41.59% | 44.76% | 45.05% | 46.54% | 4.95%

## SC3 vs SC4
SC3 vs SC4 - Critical Milestone Comparison (Week 4 Latest)
|  | SC3 Completeness |  | SC3 Timeliness |  | SC4 Completeness |  | SC4 Timeliness
Milestone | Type | Week 4 | W1→W4 | Week 4 | W1→W4 | Week 4 | W1→W4 | Week 4 | W1→W4
S02 - Collected | Actual | 79.1% | -2.2% | 31.7% | 0% | 90% | -2% | 40% | 23%
S02 - Collected | Estimated | 83.9% | 2.6% | 0% | 0% | 87% | 8% | 43% | 2%
S04 - Vessel/ flight departed | Actual | 80.1% | -6.5% | 78.1% | -7.7% | 88% | -8% | 54% | -29%
S04 - Vessel/ flight departed | Estimated | 84.6% | -2% | 68.1% | -0.7% | 97% | -2% | 43% | 5%
S07 - Vessel/ flight arrived | Actual | 86% | -4.5% | 84.9% | -3.6% | 84% | 1% | 52% | 19%
S07 - Vessel/ flight arrived | Estimated | 86.6% | -1.5% | 82.6% | -0.8% | 94% | -6% | 22% | -4%
S31 - Delivered | Actual | 58.3% | 16.1% | 9.4% | -5% | 83% | -17% | 9% | 5%
S31 - Delivered | Estimated | 70.9% | -1.3% | 46.8% | -11% | 98% | 2% | 67% | -13%
S45 - Handover to broker | Actual | 46.8% | 9.9% | 45.2% | 8.3% | 42% | -58% | 37% | -63%
S45 - Handover to broker | Estimated | 51.4% | 42.3% | 45.9% | 36.8% | N/A | N/A | N/A | N/A
SC4 Only - S00 (Shipment Created)
S00 - Shipment created | Actual | N/A | N/A | N/A | N/A | 50% | -2% | 49% | -3%

## Sheet1
Nr | Main Problems | Product Impact | Category | W01 | W02 | W03 | W04 | W05 | W06 | W07 | W08 | W09 | W10 | W11 | W12 | YTD
50 | SC3 – S02 - Collected (Estimated) | high | Timeliness (Critical) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [5 empty] | 0%
66 | SC3 – S54 - Full Container discharge (Actual) | medium | Timeliness (All) | 6.9% | 13.9% | 0% | 4.5% | 5.556% | 2.564% | 7.317% | [5 empty] | 5.82%
38 | SC4 – S05 - In delivery (Actual) | medium | Timeliness (All) | 18% | 7% | 4% | 2% | 8.852% | 5% | 7.239% | [5 empty] | 7.441%
65 | SC3 – S54 - Full Container discharge (Actual) | medium | Completeness (All) | 13.8% | 13.9% | 3.9% | 4.5% | 7.407% | 2.564% | 12.2% | [5 empty] | 8.324%
84 | For "to Door" Shipments, milestone estimates are not received 7 days before of the actual Milestone event | medium | ETA accuracy 2D | 4.4% | 13.2% | 7% | 11.5% | 12.5% | 17.4% | 17.4% | [5 empty] | 11.91%
42 | SC4 – S31 - Delivered (Actual) | high | Timeliness (Critical) | 4% | 12% | 29% | 9% | 10.53% | 16% | 13.14% | [5 empty] | 13.38%
78 | SC3 – S31 - Delivered (Actual) | high | Timeliness (Critical) | 14.4% | 15.4% | 10.1% | 9.4% | 12.79% | 18.91% | 14.14% | [5 empty] | 13.59%
87 | Milestones sent to Bosch do not follow a plausible date order | medium | Plausability (% of shipments with ≥1 sequence break) | 25.56% | 17.08% | 14.88% | 14.55% | 12.45% | 7.08% | 10.19% | [5 empty] | 14.54%
37 | SC4 – S05 - In delivery (Actual) | medium | Completeness (All) | 20% | 8% | 11% | 13% | 17.46% | 12% | 20.91% | [5 empty] | 14.63%
68 | SC3 – S51 - Arrived destination CFS (Actual) | medium | Timeliness (All) | 8.4% | 7% | 5.6% | 27.5% | 37.41% | 28% | 19.23% | [5 empty] | 19.02%
46 | SC3 – S52 - Empty Container picked up (Actual) | medium | Timeliness (All) | 19.2% | 22.2% | 25.5% | 11.5% | 24.44% | 13.04% | 25% | [5 empty] | 20.13%
24 | SC4 – S07 - Vessel/flight arrived (Estimated) | high | Timeliness (Critical) | 26% | 21% | 18% | 22% | 21.44% | 13% | 24.56% | [5 empty] | 20.86%
30 | SC4 – S18 - Recovered from carrier (Actual) | medium | Timeliness (All) | 4% | 6% | 18% | 38% | 30.59% | 38% | 39.93% | [5 empty] | 24.93%
32 | SC4 – S12 - On hand at destination Hub/CC (Actual) | medium | Timeliness (All) | 6% | 15% | 25% | 41% | 31.25% | 37% | 41.58% | [5 empty] | 28.12%
28 | SC4 – S51 - Arrived destination CFS (Actual) | medium | Timeliness (All) | 60% | 31% | 6% | 26% | 13.9% | 28% | 31.94% | [5 empty] | 28.12%
16 | SC4 – S17 - Tendered carrier (Actual) | medium | Timeliness (All) | 29% | 27% | 17% | 30% | 32.77% | 36% | 27.27% | [5 empty] | 28.43%
45 | SC3 – S52 - Empty Container picked up (Actual) | medium | Completeness (All) | 26.9% | 29.6% | 29.8% | 19.2% | 28.89% | 30.43% | 34.38% | [5 empty] | 28.46%
8 | SC4 – S46 - Documents rcvd from shipper (Actual) | medium | Timeliness (All) | 27% | 18% | 15% | 31% | 31.31% | 41% | 50.88% | [5 empty] | 30.6%
6 | SC4 – S02 - Collected (Actual) | high | Timeliness (Critical) | 17% | 39% | 34% | 40% | 32.91% | 37% | 38.34% | [5 empty] | 34.04%
48 | SC3 – S02 - Collected (Actual) | high | Timeliness (Critical) | 31.7% | 39.2% | 31.8% | 31.7% | 34.25% | 38.49% | 40.68% | [5 empty] | 35.4%
67 | SC3 – S51 - Arrived destination CFS (Actual) | medium | Completeness (All) | 41.1% | 42.6% | 31.2% | 39.9% | 42.86% | 31.33% | 22.31% | [5 empty] | 35.9%
34 | SC4 – S13 - On hand at destination SVC (Actual) | medium | Timeliness (All) | 4% | 8% | 22% | 50% | 45.39% | 61% | 65.35% | [5 empty] | 36.53%
76 | SC3 – S05 - In delivery (Actual) | medium | Timeliness (All) | 23.5% | 22.8% | 25.4% | 34.5% | 43.8% | 51.92% | 57.58% | [5 empty] | 37.07%
72 | SC3 – S45 - Handover to broker (Actual) | high | Timeliness (Critical) | 36.9% | 27.9% | 39.6% | 45.2% | 41.73% | 42.61% | 38.3% | [5 empty] | 38.89%
12 | SC4 – S11 - On hand at origin Hub/CC (Actual) | medium | Timeliness (All) | 47% | 27% | 30% | 36% | 39.81% | 45% | 53.28% | [5 empty] | 39.73%
74 | SC3 – S45 - Handover to broker (Estimated) | high | Timeliness (Critical) | 9.1% | 25% | 37.5% | 45.9% | 58.82% | 58.14% | 45.65% | [5 empty] | 40.02%
71 | SC3 – S45 - Handover to broker (Actual) | high | Completeness (Critical) | 36.9% | 27.9% | 40.6% | 46.8% | 44.09% | 46.09% | 42.55% | [5 empty] | 40.7%
83 | For "to Port" Shipments, milestone estimates are not received 7 days before of the actual Milestone event | medium | ETA accuracy 2P | 22.3% | 38.6% | 40.3% | 43.4% | 43.5% | 62.2% | 39.2% | [5 empty] | 41.36%
18 | SC4 – S50 - Received origin CFS (Actual) | medium | Timeliness (All) | 40% | 64% | 42% | 33% | 43.95% | 44% | 28.9% | [5 empty] | 42.26%
73 | SC3 – S45 - Handover to broker (Estimated) | high | Completeness (Critical) | 9.1% | 25% | 37.5% | 51.4% | 61.76% | 65.12% | 47.83% | [5 empty] | 42.53%
27 | SC4 – S51 - Arrived destination CFS (Actual) | medium | Completeness (All) | 65% | 38% | 29% | 41% | 34.98% | 40% | 58.17% | [5 empty] | 43.74%
56 | SC3 – S53 - Full Container loaded on vessel (Actual) | medium | Timeliness (All) | 37.9% | 38.9% | 49% | 34.8% | 62.96% | 55.13% | 36.59% | [5 empty] | 45.04%
4 | SC4 – S02 - Collected (Estimated) | high | Timeliness (Critical) | 41% | 36% | 34% | 43% | 52.76% | 59% | 66.59% | [5 empty] | 47.48%
20 | SC4 – S04 - Vessel/flight departed (Estimated) | high | Timeliness (Critical) | 38% | 43% | 37% | 43% | 48.77% | 53% | 72.08% | [5 empty] | 47.84%
26 | SC4 – S07 - Vessel/flight arrived (Actual) | high | Timeliness (Critical) | 33% | 66% | 61% | 52% | 43.83% | 46% | 45.58% | [5 empty] | 49.63%
70 | SC3 – S13 - On hand at destination SVC (Actual) | medium | Timeliness (All) | 6.2% | 17.3% | 36.5% | 54.5% | 72.13% | 78.7% | 84.04% | [5 empty] | 49.91%
29 | SC4 – S18 - Recovered from carrier (Actual) | medium | Completeness (All) | 23% | 13% | 31% | 61% | 63.82% | 82% | 80.53% | [5 empty] | 50.62%
55 | SC3 – S53 - Full Container loaded on vessel (Actual) | medium | Completeness (All) | 41.4% | 41.7% | 51% | 42.4% | 68.52% | 58.97% | 51.22% | [5 empty] | 50.74%
80 | SC3 – S31 - Delivered (Estimated) | high | Timeliness (Critical) | 57.8% | 58.7% | 50.4% | 46.8% | 48.45% | 45.19% | 50.17% | [5 empty] | 51.07%
75 | SC3 – S05 - In delivery (Actual) | medium | Completeness (All) | 39.6% | 52.1% | 44% | 47.8% | 55.43% | 56.73% | 64.65% | [5 empty] | 51.47%
2 | SC4 – S00 - Shipment created (Actual) | high | Timeliness (Critical) | 52% | 36% | 35% | 49% | 54.65% | 60% | 74.73% | [5 empty] | 51.63%
1 | SC4 – S00 - Shipment created (Actual) | high | Completeness (Critical) | 52% | 36% | 35% | 50% | 55.22% | 61% | 77.03% | [5 empty] | 52.32%
10 | SC4 – S10 - On hand at origin SVC (Actual) | medium | Timeliness (All) | 64% | 53% | 51% | 49% | 47.09% | 53% | 56.66% | [5 empty] | 53.39%
36 | SC4 – S45 - Handover to broker (Actual) | high | Timeliness (Critical) | 100% | 92% | 54% | 37% | 47.71% | 21% | 27.98% | [5 empty] | 54.24%
69 | SC3 – S13 - On hand at destination SVC (Actual) | medium | Completeness (All) | 8.2% | 18.3% | 41.4% | 59.6% | 80.33% | 84.26% | 90.14% | [5 empty] | 54.6%
77 | SC3 – S31 - Delivered (Actual) | high | Completeness (Critical) | 42.2% | 57.5% | 54% | 58.3% | 56.59% | 57.37% | 60.61% | [5 empty] | 55.22%
33 | SC4 – S13 - On hand at destination SVC (Actual) | medium | Completeness (All) | 28% | 14% | 34% | 66% | 70.07% | 87% | 87.79% | [5 empty] | 55.26%
52 | SC3 – S10 - On hand at origin SVC (Actual) | medium | Timeliness (All) | 65.1% | 54.8% | 58% | 49% | 59.02% | 48.15% | 53.52% | [5 empty] | 55.37%
35 | SC4 – S45 - Handover to broker (Actual) | high | Completeness (Critical) | 100% | 100% | 56% | 42% | 47.71% | 21% | 29.02% | [5 empty] | 56.53%
15 | SC4 – S17 - Tendered carrier (Actual) | medium | Completeness (All) | 70% | 42% | 42% | 57% | 59.47% | 62% | 68.92% | [5 empty] | 57.34%
14 | SC4 – S16 - Shipment booked with carrier (Actual) | medium | Timeliness (All) | 51% | 47% | 48% | 61% | 61.1% | 67% | 67.31% | [5 empty] | 57.49%
22 | SC4 – S04 - Vessel/flight departed (Actual) | high | Timeliness (Critical) | 83% | 55% | 52% | 54% | 49.15% | 58% | 63.43% | [5 empty] | 59.22%
82 | SC3 – S55 - Empty Container returned (Actual) | medium | Timeliness (All) | 25% | 55.6% | 52% | 62.5% | 76.92% | 77.92% | 67.5% | [5 empty] | 59.64%
7 | SC4 – S46 - Documents rcvd from shipper (Actual) | medium | Completeness (All) | 61% | 37% | 41% | 61% | 67.74% | 73% | 82.16% | [5 empty] | 60.41%
31 | SC4 – S12 - On hand at destination Hub/CC (Actual) | medium | Completeness (All) | 28% | 34% | 49% | 73% | 69.74% | 87% | 84.49% | [5 empty] | 60.75%
54 | SC3 – S50 - Received origin CFS (Actual) | medium | Timeliness (All) | 70.1% | 71.3% | 67.2% | 65.4% | 70.75% | 49.33% | 42.31% | [5 empty] | 62.34%
81 | SC3 – S55 - Empty Container returned (Actual) | medium | Completeness (All) | 35.7% | 66.7% | 62% | 65.6% | 76.92% | 79.22% | 68.75% | [5 empty] | 64.98%
11 | SC4 – S11 - On hand at origin Hub/CC (Actual) | medium | Completeness (All) | 68% | 44% | 46% | 68% | 70.87% | 82% | 88.79% | [5 empty] | 66.81%
79 | SC3 – S31 - Delivered (Estimated) | high | Completeness (Critical) | 72.2% | 76.4% | 69.4% | 70.9% | 67.05% | 64.74% | 65.66% | [5 empty] | 69.48%
85 | Milestones received by Bosch do not contain the CIV or DN reference | high | Reference Completeness (SC4) | 71.4% | 63.8% | 72% | 70.2% | 67.9% | 75.2% | 77.7% | [5 empty] | 71.17%
40 | SC4 – S31 - Delivered (Estimated) | high | Timeliness (Critical) | 80% | 82% | 70% | 67% | 68.9% | 67% | 72.65% | [5 empty] | 72.51%
60 | SC3 – S04 - Vessel/flight departed (Estimated) | high | Timeliness (Critical) | 68.8% | 72.4% | 70.6% | 68.1% | 81.21% | 70.77% | 76.09% | [5 empty] | 72.57%
53 | SC3 – S50 - Received origin CFS (Actual) | medium | Completeness (All) | 78.5% | 78.3% | 77.6% | 69.3% | 79.59% | 64% | 60.77% | [5 empty] | 72.58%
13 | SC4 – S16 - Shipment booked with carrier (Actual) | medium | Completeness (All) | 71% | 61% | 61% | 75% | 76.85% | 79% | 84.28% | [5 empty] | 72.59%
47 | SC3 – S02 - Collected (Actual) | high | Completeness (Critical) | 81.3% | 79.2% | 73% | 79.1% | 75.68% | 78.62% | 77.95% | [5 empty] | 77.84%
17 | SC4 – S50 - Received origin CFS (Actual) | medium | Completeness (All) | 90% | 92% | 77% | 71% | 78.92% | 67% | 87.07% | [5 empty] | 80.43%
49 | SC3 – S02 - Collected (Estimated) | high | Completeness (Critical) | 81.3% | 80.9% | 77.7% | 83.9% | 83% | 84.88% | 86.43% | [5 empty] | 82.59%
41 | SC4 – S31 - Delivered (Actual) | high | Completeness (Critical) | 100% | 100% | 76% | 83% | 83.97% | 66% | 71.58% | [5 empty] | 82.94%
58 | SC3 – S04 - Vessel/flight departed (Actual) | high | Timeliness (Critical) | 85.8% | 85.8% | 81.7% | 78.1% | 89.09% | 83.06% | 80.76% | [5 empty] | 83.47%
64 | SC3 – S07 - Vessel/flight arrived (Estimated) | high | Timeliness (Critical) | 83.4% | 86.4% | 83% | 82.6% | 89.09% | 82.79% | 79.3% | [5 empty] | 83.8%
25 | SC4 – S07 - Vessel/flight arrived (Actual) | high | Completeness (Critical) | 83% | 83% | 81% | 84% | 81.78% | 88% | 86.22% | [5 empty] | 83.86%
57 | SC3 – S04 - Vessel/flight departed (Actual) | high | Completeness (Critical) | 86.6% | 86.4% | 84.3% | 80.1% | 91.21% | 84.97% | 82.51% | [5 empty] | 85.16%
3 | SC4 – S02 - Collected (Estimated) | high | Completeness (Critical) | 79% | 83% | 85% | 87% | 84.67% | 90% | 88.57% | [5 empty] | 85.32%
59 | SC3 – S04 - Vessel/flight departed (Estimated) | high | Completeness (Critical) | 86.6% | 89.5% | 86.3% | 84.6% | 91.21% | 83.88% | 83.97% | [5 empty] | 86.58%
62 | SC3 – S07 - Vessel/flight arrived (Actual) | high | Timeliness (Critical) | 88.5% | 88.9% | 85% | 84.9% | 93.03% | 86.34% | 87.76% | [5 empty] | 87.77%
9 | SC4 – S10 - On hand at origin SVC (Actual) | medium | Completeness (All) | 96% | 91% | 83% | 88% | 81.31% | 90% | 91.54% | [5 empty] | 88.69%
61 | SC3 – S07 - Vessel/flight arrived (Actual) | high | Completeness (Critical) | 90.5% | 90.1% | 86.3% | 86% | 93.33% | 87.43% | 88.34% | [5 empty] | 88.86%
63 | SC3 – S07 - Vessel/flight arrived (Estimated) | high | Completeness (Critical) | 88.1% | 91.3% | 87.9% | 86.6% | 93.64% | 88.8% | 88.34% | [5 empty] | 89.24%
21 | SC4 – S04 - Vessel/flight departed (Actual) | high | Completeness (Critical) | 96% | 93% | 83% | 88% | 89.37% | 88% | 92.76% | [5 empty] | 90.02%
5 | SC4 – S02 - Collected (Actual) | high | Completeness (Critical) | 92% | 95% | 88% | 90% | 88.94% | 90% | 90.81% | [5 empty] | 90.68%
51 | SC3 – S10 - On hand at origin SVC (Actual) | medium | Completeness (All) | 94.5% | 93.3% | 89.5% | 88.9% | 93.44% | 90.28% | 90.14% | [5 empty] | 91.44%
44 | SC3 – S60 - Pre-Booking confirmed (Actual) | medium | Timeliness (All) | 93.1% | 91.7% | 92.2% | 93.9% | 92.31% | 92.11% | 90.54% | [5 empty] | 92.26%
43 | SC3 – S60 - Pre-Booking confirmed (Actual) | medium | Completeness (All) | 93.1% | 91.7% | 92.2% | 95.5% | 92.31% | 92.11% | 93.24% | [5 empty] | 92.88%
23 | SC4 – S07 - Vessel/flight arrived (Estimated) | high | Completeness (Critical) | 100% | 96% | 93% | 94% | 92.79% | 96% | 97.53% | [5 empty] | 95.62%
39 | SC4 – S31 - Delivered (Estimated) | high | Completeness (Critical) | 96% | 99% | 97% | 98% | 95.69% | 94% | 95.17% | [5 empty] | 96.41%
19 | SC4 – S04 - Vessel/flight departed (Estimated) | high | Completeness (Critical) | 99% | 99% | 96% | 97% | 95.64% | 97% | 95.76% | [5 empty] | 97.06%
86 | Milestone containing CIV or DN reference do not have the correct data | medium | Reference Quality (SC4) | [12 empty] | #DIV/0!

## 5Why
Please find further information behind cell comments.
5 Why Form
| 8D Title | [5 empty] | Complaint No.
| Bosch Part | [5 empty] | Date
Version
|  | The problem with which the 5Why question chain is started | 1st Why? | 2nd Why? | 3rd Why? | 4th Why? | 5th Why? | …. | … | Root Causes (TRC, MRC) | Measures (R, D)
1) Why did it happen? (Why did the manufacturing process not prevent the incident? ) |  | Milestones are not being sent to Bosch | Q:why are not being sent? A:Because are blocked in the system sending the EDI message | Q:why are they blocked? A:because messages do not have all info needed to be sent | Q:why do not have all info? A:because they are not being inserted in the TMS | Q:why are they not being inserted? A:because the operating system allows to leave some fields blank | Q:why is it possible? A:because the system is not configured to make them compulsory to trigger the milestones |  |  | TRC: EDI milestone trigger lacks validation for mandatory fields; configuration permits blank critical fields. MRC: EDI requirements/configuration governance is missing (no owner / review gate). | R: EDI/IT Lead + Operations Process Owner D: 2026-03-31 Action: Configure mandatory fields & validation rules for milestone triggers; run regression test; deploy to production; communicate update to users.
|  | Milestones are not being sent to Bosch on time | Q:why are not being sent on time? A:because the milestones are not all milestones triggered automatically by the system requiring manual timely inputs | Q:why are they not auto triggered for all? A:because there is a mix of manual bookings and automated bookings | Q:why are there manual bookings? A:manual bookings are expected however the % of manual bookings were higher than planned. | Q:why are manual bookings higher than planned? A:the planned forecast during implementation was close to 80% and reality was lower.
|  | Milestones received by Bosch do not contain the CIV or DN reference and not the correct data | Q:why are references incorrect or lack the correct data? A:These fields are only for SC4 bookings and expected to be manually entered and hence prone to errors. | Q:why are errors happening in the manual process? A:because the operators are not following the SOPs to put in the appropriate information in time | Q: Why are the operators not following SOPs? A:because they are not prioritizing this effort versus delivering other items such as making deliverings and exiting CMT | Q:why are they not prioritizing? A:because the team is whort on capacity | Q:why are they short in capacity? A:because expectations was to have lower SC4 bookings in the plan and staffing was not adjusted
|  | For "to Port" and "to Door" Shipments, milestone estimates are not received 7 days before of the actual Milestone event | Q:why are they not received 7 days before? A:The event is updated either too early or too late before the event missing the 7 days | Q:why is it too early to too late? A:the Maersk Liner integration is automated, but the message is not transmitted to the customer | Q: Why not transmitted? A: message is not be triggered from TMS to EDI each time the vessel update is received. | Q:why is message not triggered? A:there will be way too many updates and there is logic to prevent too many messages being sent
|  | Milestones sent to Bosch do not follow a plausible date order | Q: why do milestones not follow a plausible date order? A: because some milestone timestamps are sent with incorrect or placeholder values that break the expected S02→S04→S07→S31 sequence | Q: why are timestamps incorrect? A: because retroactive corrections and system-generated default dates (e.g., 1900 placeholders) are transmitted without plausibility validation | Q: why are defaults transmitted? A: because the EDI system does not filter out placeholder dates or validate chronological order before sending | Q: why is there no chronological validation? A: because the IFTSTA message builder was not configured with sequence-aware validation rules | Q: why was it not configured? A: because plausibility was assumed to be the responsibility of the source operating system, not the EDI layer | Q: why was this assumption made? A: because the boundary of data quality responsibility between ops systems and EDI was not clearly defined |  | TRC: EDI system lacks chronological sequence validation; transmits placeholder dates and retroactive corrections without plausibility checks. MRC: Data quality responsibility boundary between source systems and EDI layer was not defined. | R: EDI/IT Lead + Data Quality Team D: 2026-04-30 Action: Implement pre-transmission plausibility check (S02<S04<S07<S31); reject/flag milestones with 1900 placeholder dates; add sequence validation to IFTSTA builder; weekly plausibility KPI report.
|  | Critical milestones are not being sent to Bosch | Q:why wasn't noticed? A:because there are no dashboard or checks | Q:why there are no checks? A:because they were not implemented | Q:why were they not implemented? A:because are not part of the process of onboarding a client | Q:why are not part of the process? A:because there wasn't build a system to programatically extract data from the EDI system | Q:why wasn't built? A:because it wasn't prioritised | Q: why wasn't it prioritised? A: because there was no monitoring KPI showing customer impact/cost of missing milestones | Q: why was there no KPI? A: because EDI performance governance and reporting ownership were not defined | TRC: No monitoring/alerting for missing milestone transmissions. MRC: Monitoring and reporting were not included in the customer onboarding scope/prioritisation. | R: Ops Excellence + IT/BI D: 2026-03-31 Action: Build dashboard + daily exception report for missing/failed EDI messages; set alert thresholds; assign owner to review exceptions.
Note on E14: waf2abt: e.g. the direct cause from Ishikawa analysis